## DIM_Projects
ProjectID | ProjectName | Programme | Portfolio | Department | ProjectManager | SponsorName | ProjectType | Priority | StartDate | PlannedEndDate | ActualEndDate | Phase | RAGStatus | StrategicObjective | Region | IsActive
P001 | Customer Portal Modernisation | Digital Transformation | ECS Portfolio | Digital & IT | Sarah Chen | Mark Hughes | New Development | High | 2026-01-05 | 2026-09-30 |  | Execution | Green | Improve customer digital experience | GB - England | TRUE
P002 | Azure Cloud Infrastructure Migration | Infrastructure | ECS Portfolio | IT Operations | Ariful Haque | Mark Hughes | Migration | High | 2026-02-01 | 2026-12-31 |  | Planning | Amber | Cloud-first infrastructure strategy | GB - England | TRUE
P003 | ECS Portfolio Reporting Automation | PMO | ECS Portfolio | IT PMO | Ariful Haque | Lisa Ward | Process Improvement | Medium | 2026-01-15 | 2026-06-30 |  | Execution | Green | Data-driven portfolio governance | GB - England | TRUE
P004 | Smart Meter Data Platform Upgrade | Data & Analytics | ECS Portfolio | Data Engineering | James Patel | Lisa Ward | Enhancement | High | 2026-03-01 | 2026-10-31 |  | Initiation | Red | Enable real-time energy analytics | GB - Scotland | TRUE
P005 | Cyber Security Compliance Programme | Security | ECS Portfolio | IT Security | Nina Sharma | Mark Hughes | Compliance | Critical | 2026-01-01 | 2026-07-31 |  | Execution | Amber | Regulatory compliance & risk reduction | GB - England | TRUE
P006 | Field Operations Mobile App | Field Services | Operations Portfolio | Field Operations | Tom Bradley | Rachel Evans | New Development | Medium | 2025-10-01 | 2026-05-31 | 2026-04-15 | Closed | Green | Improve field engineer productivity | GB - Wales | FALSE
P007 | HR Self-Service Portal | Corporate Systems | Corporate Portfolio | Human Resources | Emma Collins | Rachel Evans | New Development | Low | 2026-04-01 | 2026-11-30 |  | Initiation | Green | Reduce HR admin overhead | GB - England | TRUE
P008 | SAP Finance Module Upgrade | Finance Systems | Corporate Portfolio | Finance & IT | David Kim | Simon Grant | Upgrade | High | 2025-11-01 | 2026-06-30 |  | Execution | Red | Modernise core finance platform | GB - England | TRUE
P009 | Network Infrastructure Refresh | Infrastructure | Operations Portfolio | IT Operations | James Patel | Simon Grant | Refresh | Medium | 2026-02-15 | 2026-08-31 |  | Planning | Green | Replace end-of-life network hardware | GB - Scotland | TRUE
P010 | Customer Data Analytics Platform | Data & Analytics | ECS Portfolio | Data Engineering | Sarah Chen | Mark Hughes | New Development | High | 2026-05-01 | 2026-12-31 |  | Initiation | Green | Unlock customer insight capabilities | GB - England | TRUE

## Variance Analysis Report
ECS PORTFOLIO — MONTHLY VARIANCE ANALYSIS REPORT ¦ April 2026 ¦ Prepared by: Ariful Haque
All figures in GBP (£) ¦ Source: FACT_Budget ¦ Report date: 04 May 2026
Total Baseline Budget |  | Total Actual Spend |  | Total EAC |  | Total Variance |  | Portfolio Variance %
Total Baseline Budget |  | Total Actual Spend |  | Total EAC |  | Total Variance |  | Portfolio Variance %
5032000 |  | 726100 |  | 5075100 |  | 0 |  | #DIV/0!
PROJECT-BY-PROJECT VARIANCE ANALYSIS — APRIL 2026 (LATEST SNAPSHOT)
Project ID | Project Name | Baseline Budget | Actual Spend to Date | Forecast to Complete | EAC | Budget Variance | Variance % | RAG Status | Trend
P001 | Customer Portal Modernisation | 285000 | 56700 | 211000 | 267700 | 17300 | 6.07% | Green | Stable
P002 | Azure Cloud Infrastructure Migration | 420000 | 47125 | 377500 | 424625 | -4625 | -1.101% | Green | Worsening
P003 | ECS Portfolio Reporting Automation | 95000 | 25425 | 67000 | 92425 | 2575 | 2.711% | Green | Stable
P004 | Smart Meter Data Platform Upgrade | 380000 | 24150 | 378250 | 402400 | -22400 | -5.895% | Amber | Worsening
P005 | Cyber Security Compliance Programme | 78000 | 28125 | 53500 | 81625 | -3625 | -4.647% | Green | Stable
P008 | SAP Finance Module Upgrade | 480000 | 179750 | 363750 | 543500 | -63500 | -13.23% | Red | Critical
PORTFOLIO TOTAL |  | 1738000 | 361275 | 1451000 | 1812275 | -74275 | -4.274% | Green
BOARD NARRATIVE — PORTFOLIO FINANCIAL COMMENTARY ¦ April 2026
Overall Portfolio Status:
The ECS portfolio is tracking an overall adverse variance of £99,000 against a combined baseline of £1,598,000 as at end of April 2026, representing a 6% overspend at portfolio level. Two projects require immediate Programme Director attention.
P004 — Smart Meter Data Platform (RED — WORSENING):
P004 is tracking £33,000 over baseline, representing a 9% adverse variance against the £380,000 approved budget. The primary driver is integration complexity underscoped at business case stage, resulting in higher-than-planned contractor hours across all four reported months. The variance is worsening month on month — January showed £17,500 adverse, growing to £33,000 in April — indicating a structural rather than timing issue. An options paper has been submitted to the Programme Director with three courses of action: re-baseline, de-scope, or accelerated root cause investigation. Decision required by 15 May 2026.
P008 — SAP Finance Module Upgrade (RED — CRITICAL):
P008 is tracking £68,000 over baseline, representing a 21% adverse variance against the £320,000 approved budget — the most significant variance in the portfolio. The overspend has accelerated from £14,000 in November 2025 to £68,000 by April 2026 due to undiscovered SAP integration dependencies requiring an additional discovery sprint. The revised go-live date of 21 July 2026 also conflicts with the finance period-end close. A change request has been raised and is pending Programme Board approval. Immediate decision required on revised budget and timeline.
Projects On Track
P001 (Customer Portal Modernisation) and P003 (ECS Portfolio Reporting Automation) are both tracking within acceptable variance thresholds at 6% and 2% respectively. P001 received an approved change of £15,000 in April which has been reflected in the revised baseline.

## FACT_Budget
BudgetID | ProjectID | SnapshotMonth | SnapshotYear | Period | BaselineBudget_GBP | ApprovedChanges_GBP | RevisedBudget_GBP | ActualSpend_GBP | CommittedSpend_GBP | ForecastToComplete_GBP | EAC_GBP | BudgetVariance_GBP | VariancePct | CapexActual_GBP | OpexActual_GBP | ResourceCost_GBP | LicenceCost_GBP | InfrastructureCost_GBP
B001 | P001 | January | 2026 | 2026-01 | 285000 | 0 | 285000 | 18500 | 24000 | 242000 | 260500 | 24500 | 8.596% | 11000 | 7500 | 14000 | 2000 | 2500
B002 | P001 | February | 2026 | 2026-02 | 285000 | 0 | 285000 | 41200 | 54000 | 219000 | 260200 | 24800 | 8.7% | 24000 | 17200 | 31000 | 4500 | 5700
B003 | P001 | March | 2026 | 2026-03 | 285000 | 0 | 285000 | 68900 | 82000 | 198000 | 266900 | 18100 | 6.3% | 40000 | 28900 | 52000 | 7500 | 9400
B004 | P001 | April | 2026 | 2026-04 | 285000 | 15000 | 300000 | 98200 | 112000 | 185000 | 283200 | 16800 | 5.6% | 57000 | 41200 | 74000 | 11000 | 13200
B005 | P002 | January | 2026 | 2026-01 | 420000 | 0 | 420000 | 12000 | 18000 | 402000 | 414000 | 6000 | 1.4% | 10000 | 2000 | 9000 | 1500 | 1500
B006 | P002 | February | 2026 | 2026-02 | 420000 | 0 | 420000 | 31500 | 45000 | 385000 | 416500 | 3500 | 0.8% | 26000 | 5500 | 23000 | 4000 | 4500
B007 | P002 | March | 2026 | 2026-03 | 420000 | 0 | 420000 | 58000 | 75000 | 375000 | 433000 | -13000 | -3.1% | 48000 | 10000 | 42000 | 7000 | 9000
B008 | P002 | April | 2026 | 2026-04 | 420000 | 0 | 420000 | 87000 | 105000 | 348000 | 435000 | -15000 | -3.6% | 72000 | 15000 | 63000 | 10500 | 13500
B009 | P003 | January | 2026 | 2026-01 | 95000 | 0 | 95000 | 8200 | 11000 | 84000 | 92200 | 2800 | 2.9% | 0 | 8200 | 7500 | 500 | 200
B010 | P003 | February | 2026 | 2026-02 | 95000 | 0 | 95000 | 19500 | 24000 | 73000 | 92500 | 2500 | 2.6% | 0 | 19500 | 18000 | 1000 | 500
B011 | P003 | March | 2026 | 2026-03 | 95000 | 0 | 95000 | 31200 | 37000 | 61000 | 92200 | 2800 | 2.9% | 0 | 31200 | 29000 | 1500 | 700
B012 | P003 | April | 2026 | 2026-04 | 95000 | 0 | 95000 | 42800 | 50000 | 50000 | 92800 | 2200 | 2.3% | 0 | 42800 | 40000 | 2000 | 800
B013 | P004 | January | 2026 | 2026-01 | 380000 | 0 | 380000 | 5500 | 9000 | 392000 | 397500 | -17500 | -4.6% | 4000 | 1500 | 4000 | 800 | 700
B014 | P004 | February | 2026 | 2026-02 | 380000 | 0 | 380000 | 14200 | 22000 | 381000 | 395200 | -15200 | -4% | 10000 | 4200 | 10500 | 2000 | 1700
B015 | P004 | March | 2026 | 2026-03 | 380000 | 0 | 380000 | 28900 | 42000 | 375000 | 403900 | -23900 | -6.3% | 20000 | 8900 | 21000 | 4000 | 3900
B016 | P004 | April | 2026 | 2026-04 | 380000 | 0 | 380000 | 48000 | 64000 | 365000 | 413000 | -33000 | -8.7% | 33000 | 15000 | 35000 | 6500 | 6500
B017 | P005 | January | 2026 | 2026-01 | 78000 | 0 | 78000 | 9800 | 13000 | 70000 | 79800 | -1800 | -2.3% | 0 | 9800 | 8000 | 1200 | 600
B018 | P005 | February | 2026 | 2026-02 | 78000 | 0 | 78000 | 21500 | 28000 | 59000 | 80500 | -2500 | -3.2% | 0 | 21500 | 18000 | 2500 | 1000
B019 | P005 | March | 2026 | 2026-03 | 78000 | 0 | 78000 | 34200 | 42000 | 47000 | 81200 | -3200 | -4.1% | 0 | 34200 | 28000 | 4000 | 2200
B020 | P005 | April | 2026 | 2026-04 | 78000 | 5000 | 83000 | 47000 | 56000 | 38000 | 85000 | -2000 | -2.4% | 0 | 47000 | 38000 | 6000 | 3000
B021 | P006 | October | 2025 | 2025-10 | 145000 | 0 | 145000 | 28000 | 35000 | 112000 | 140000 | 5000 | 3.4% | 15000 | 13000 | 21000 | 4000 | 3000
B022 | P006 | November | 2025 | 2025-11 | 145000 | 0 | 145000 | 62000 | 72000 | 80000 | 142000 | 3000 | 2.1% | 33000 | 29000 | 47000 | 9000 | 6000
B023 | P006 | December | 2025 | 2025-12 | 145000 | 0 | 145000 | 98000 | 108000 | 44000 | 142000 | 3000 | 2.1% | 52000 | 46000 | 74000 | 14000 | 10000
B024 | P006 | January | 2026 | 2026-01 | 145000 | 0 | 145000 | 118000 | 125000 | 22000 | 140000 | 5000 | 3.4% | 63000 | 55000 | 89000 | 17000 | 12000
B025 | P006 | February | 2026 | 2026-02 | 145000 | 0 | 145000 | 138500 | 142000 | 4000 | 142500 | 2500 | 1.7% | 74000 | 64500 | 104000 | 20000 | 14500
B026 | P006 | March | 2026 | 2026-03 | 145000 | 0 | 145000 | 143200 | 143200 | 0 | 143200 | 1800 | 1.2% | 76000 | 67200 | 108000 | 21000 | 14200
B027 | P008 | November | 2025 | 2025-11 | 320000 | 0 | 320000 | 22000 | 30000 | 312000 | 334000 | -14000 | -4.4% | 18000 | 4000 | 16000 | 3500 | 2500
B028 | P008 | December | 2025 | 2025-12 | 320000 | 0 | 320000 | 55000 | 68000 | 295000 | 350000 | -30000 | -9.4% | 45000 | 10000 | 41000 | 8000 | 6000
B029 | P008 | January | 2026 | 2026-01 | 320000 | 0 | 320000 | 94000 | 112000 | 265000 | 359000 | -39000 | -12.2% | 77000 | 17000 | 70000 | 14000 | 10000
B030 | P008 | February | 2026 | 2026-02 | 320000 | 0 | 320000 | 138000 | 160000 | 228000 | 366000 | -46000 | -14.4% | 113000 | 25000 | 103000 | 20000 | 15000
B031 | P008 | March | 2026 | 2026-03 | 320000 | 0 | 320000 | 182000 | 210000 | 195000 | 377000 | -57000 | -17.8% | 149000 | 33000 | 136000 | 27000 | 19000
B032 | P008 | April | 2026 | 2026-04 | 320000 | 0 | 320000 | 228000 | 260000 | 160000 | 388000 | -68000 | -21.3% | 186000 | 42000 | 170000 | 34000 | 24000

## FACT_Milestones
MilestoneID | ProjectID | MilestoneName | MilestoneType | PlannedDate | ActualDate | ForecastDate | Status | DaysVariance | WeightPct | IsCriticalPath | Notes
M001 | P001 | Project Kickoff | Gate | 2026-01-05 | 2026-01-05 | 2026-01-05 | Achieved | 0 | 5 | TRUE | Delivered on time. All stakeholders aligned.
M002 | P001 | SSO Integration Complete | Delivery | 2026-03-31 | 2026-03-28 | 2026-03-28 | Achieved | -3 | 15 | TRUE | Delivered 3 days early. MSAL testing passed.
M003 | P001 | Dashboard Redesign Complete | Delivery | 2026-05-31 |  | 2026-06-07 | At Risk | 7 | 20 | TRUE | BUG-02 mobile performance issue adding 1 week.
M004 | P001 | UAT Sign-off | Gate | 2026-07-31 |  | 2026-08-14 | At Risk | 14 | 25 | TRUE | Dependent on Dashboard milestone. Cascading delay risk.
M005 | P001 | Go-Live | Gate | 2026-09-30 |  | 2026-09-30 | On Track | 0 | 35 | TRUE | Contingency absorbed earlier slippage.
M006 | P002 | Cloud Strategy Approved | Gate | 2026-02-28 | 2026-02-25 | 2026-02-25 | Achieved | -3 | 10 | FALSE | Board approval received early.
M007 | P002 | Azure Landing Zone Live | Delivery | 2026-05-01 |  | 2026-05-15 | At Risk | 14 | 25 | TRUE | Well-Architected Review delayed pending resource.
M008 | P002 | Pilot Migration Complete (10 servers) | Delivery | 2026-07-31 |  | 2026-07-31 | On Track | 0 | 30 | TRUE | Pilot scope agreed. Team confirmed.
M009 | P002 | Full Migration Complete | Gate | 2026-12-31 |  | 2026-12-31 | On Track | 0 | 35 | TRUE | Dependent on successful pilot.
M010 | P003 | Power BI Connector Live | Delivery | 2026-03-31 | 2026-03-29 | 2026-03-29 | Achieved | -2 | 30 | TRUE | OData feed stable. Data refresh confirmed.
M011 | P003 | Automated MI Pack Deployed | Delivery | 2026-05-31 |  | 2026-05-31 | On Track | 0 | 40 | TRUE | On track. DAX measures in final review.
M012 | P003 | RAID Reporting Live in ADO | Delivery | 2026-06-30 |  | 2026-06-30 | On Track | 0 | 30 | TRUE | Work item types configured in ADO tenant.
M013 | P004 | Business Case Approved | Gate | 2026-03-31 |  | 2026-04-28 | Delayed | 28 | 20 | TRUE | Finance challenged ROI assumptions. Rework required.
M014 | P004 | Data Architecture Design Complete | Delivery | 2026-05-31 |  | 2026-06-30 | At Risk | 30 | 25 | TRUE | Dependent on business case approval.
M015 | P004 | Smart Meter API Integration | Delivery | 2026-08-31 |  | 2026-09-30 | At Risk | 30 | 30 | TRUE | Supplier API access provisioning delayed.
M016 | P004 | Platform Go-Live | Gate | 2026-10-31 |  | 2026-11-30 | At Risk | 30 | 25 | TRUE | Cumulative delay from earlier milestones.
M017 | P005 | Security Assessment Complete | Delivery | 2026-02-28 | 2026-02-26 | 2026-02-26 | Achieved | -2 | 20 | FALSE | All 47 controls assessed. 8 gaps identified.
M018 | P005 | Remediation Plan Approved | Gate | 2026-03-31 | 2026-03-31 | 2026-03-31 | Achieved | 0 | 15 | TRUE | Plan signed off by CISO.
M019 | P005 | Critical Controls Remediated | Delivery | 2026-06-30 |  | 2026-06-30 | On Track | 0 | 40 | TRUE | 6 of 8 gaps on track. 2 need supplier action.
M020 | P005 | Compliance Audit Passed | Gate | 2026-07-31 |  | 2026-07-31 | On Track | 0 | 25 | TRUE | External auditor booked for w/c 28 July.
M021 | P006 | App Development Complete | Delivery | 2026-03-31 | 2026-03-28 | 2026-03-28 | Achieved | -3 | 30 | FALSE | Final sprint delivered ahead of schedule.
M022 | P006 | Field UAT Complete | Delivery | 2026-04-10 | 2026-04-08 | 2026-04-08 | Achieved | -2 | 30 | FALSE | Field engineers signed off. 2 minor bugs logged.
M023 | P006 | Go-Live | Gate | 2026-04-30 | 2026-04-15 | 2026-04-15 | Achieved | -15 | 40 | FALSE | Delivered 2 weeks early. Strong field adoption.
M024 | P008 | Design Complete | Delivery | 2025-12-31 | 2025-12-29 | 2025-12-29 | Achieved | -2 | 15 | TRUE
M025 | P008 | Build Complete | Delivery | 2026-03-31 |  | 2026-04-21 | Delayed | 21 | 25 | TRUE | Integration complexity higher than scoped. Change request raised.
M026 | P008 | System Integration Testing | Delivery | 2026-05-15 |  | 2026-06-05 | Delayed | 21 | 25 | TRUE | Cascading from build delay.
M027 | P008 | Go-Live | Gate | 2026-06-30 |  | 2026-07-21 | Delayed | 21 | 35 | TRUE | Finance blackout period means earliest go-live is 21 July.

## FACT_SprintVelocity
VelocityID | ProjectID | SprintNumber | SprintName | SprintStartDate | SprintEndDate | CommittedPoints | CompletedPoints | CarryOverPoints | BugsRaised | BugsResolved | TeamCapacityDays | ActualCapacityDays | VelocityTrend | SprintGoalMet
V001 | P001 | 1 | Sprint 1 – SSO Foundation | 2026-01-19 | 2026-02-01 | 32 | 30 | 2 | 3 | 2 | 80 | 78 | Stable | Yes
V002 | P001 | 2 | Sprint 2 – SSO Complete | 2026-02-02 | 2026-02-15 | 34 | 34 | 0 | 1 | 3 | 80 | 80 | Up | Yes
V003 | P001 | 3 | Sprint 3 – Dashboard Start | 2026-02-16 | 2026-03-01 | 38 | 35 | 3 | 4 | 2 | 80 | 74 | Down | No
V004 | P001 | 4 | Sprint 4 – Dashboard Core | 2026-03-02 | 2026-03-15 | 36 | 36 | 0 | 2 | 4 | 80 | 80 | Up | Yes
V005 | P001 | 5 | Sprint 5 – API Integration | 2026-03-16 | 2026-03-29 | 40 | 38 | 2 | 5 | 3 | 80 | 76 | Stable | Yes
V006 | P001 | 6 | Sprint 6 – Mobile & UAT Prep | 2026-03-30 | 2026-04-12 | 38 | 28 | 10 | 8 | 5 | 80 | 72 | Down | No
V007 | P003 | 1 | Sprint 1 – ADO Connector | 2026-01-19 | 2026-02-01 | 20 | 20 | 0 | 0 | 0 | 40 | 40 | Stable | Yes
V008 | P003 | 2 | Sprint 2 – Power BI Model | 2026-02-02 | 2026-02-15 | 22 | 22 | 0 | 1 | 1 | 40 | 40 | Up | Yes
V009 | P003 | 3 | Sprint 3 – RAG Dashboard | 2026-02-16 | 2026-03-01 | 24 | 23 | 1 | 0 | 0 | 40 | 38 | Stable | Yes
V010 | P003 | 4 | Sprint 4 – Velocity & Burndown | 2026-03-02 | 2026-03-15 | 22 | 22 | 0 | 0 | 1 | 40 | 40 | Up | Yes
V011 | P003 | 5 | Sprint 5 – RAID Reporting | 2026-03-16 | 2026-03-29 | 25 | 24 | 1 | 0 | 0 | 40 | 40 | Stable | Yes
V012 | P003 | 6 | Sprint 6 – MI Pack Automation | 2026-03-30 | 2026-04-12 | 24 | 24 | 0 | 1 | 0 | 40 | 40 | Up | Yes
V013 | P005 | 1 | Sprint 1 – Assessment | 2026-01-05 | 2026-01-18 | 28 | 26 | 2 | 0 | 0 | 60 | 58 | Stable | No
V014 | P005 | 2 | Sprint 2 – Gap Analysis | 2026-01-19 | 2026-02-01 | 30 | 30 | 0 | 0 | 0 | 60 | 60 | Up | Yes
V015 | P005 | 3 | Sprint 3 – Remediation Plan | 2026-02-02 | 2026-02-15 | 32 | 31 | 1 | 2 | 2 | 60 | 58 | Stable | Yes
V016 | P005 | 4 | Sprint 4 – Controls (Batch 1) | 2026-02-16 | 2026-03-01 | 30 | 30 | 0 | 1 | 1 | 60 | 60 | Up | Yes
V017 | P005 | 5 | Sprint 5 – Controls (Batch 2) | 2026-03-02 | 2026-03-15 | 32 | 29 | 3 | 3 | 2 | 60 | 55 | Down | No
V018 | P005 | 6 | Sprint 6 – Audit Prep | 2026-03-16 | 2026-03-29 | 28 | 28 | 0 | 0 | 3 | 60 | 60 | Up | Yes

## FACT_RAID
RAID_ID | ProjectID | RAIDType | Title | Category | Severity | Probability | RAGStatus | Owner | RaisedDate | DueDate | ClosedDate | Status | DaysOpen | FinancialImpact_GBP | DeliveryImpactDays | MitigationAction
RAID-001 | P001 | Risk | Azure AD rate limit under peak load | Technical | High | High | Red | James Patel | 2026-01-20 | 2026-05-15 |  | Open | 99 | 25000 | 14 | Load test to 60k concurrent users. Engage Microsoft for rate limit uplift.
RAID-002 | P001 | Risk | Smart Meter API downtime risk | Technical | Medium | Medium | Amber | Dev Team B | 2026-02-10 | 2026-04-30 |  | Open | 78 | 8000 | 5 | Implement caching. Show 'Data as of [timestamp]' when API unavailable.
RAID-003 | P001 | Issue | BUG-01: SSO fails for special character UPN | Technical | Critical |  | Red | James Patel | 2026-04-01 | 2026-04-14 |  | In Progress | 28 | 5000 | 7 | Hotfix encoding UPN before MSAL token request. Due 14 April.
RAID-004 | P001 | Risk | Key developer departure risk | Resource | High | Low | Amber | Programme Manager | 2026-02-15 | 2026-04-20 |  | Open | 73 | 35000 | 21 | Knowledge transfer sessions. Confluence documentation. Cross-train backup.
RAID-005 | P001 | Dependency | Smart Meter API access from Data Platform | External |  |  | Amber | Dev Team B | 2026-04-10 | 2026-04-25 |  | Open | 19 | 0 | 14 | Escalated to Data Platform lead. Provisional access expected 25 April.
RAID-006 | P002 | Risk | Azure Landing Zone delayed by resource gap | Technical | High | Medium | Red | Cloud Admin | 2026-03-01 | 2026-05-01 |  | Open | 59 | 18000 | 14 | Engage specialist contractor. Target Landing Zone by 15 May.
RAID-007 | P002 | Assumption | Existing network VLAN config compatible with Azure | Technical |  |  | Amber | James Patel | 2026-02-01 | 2026-04-15 |  | Open | 87 | 0 | 0 | Validate with network team by 15 April. Raise as risk if incompatible.
RAID-008 | P002 | Risk | Migration scope growth — servers 30% above estimate | Scope | High | High | Red | Ariful Haque | 2026-03-20 | 2026-05-31 |  | Open | 40 | 42000 | 30 | Re-baseline migration scope. Raise change request with revised timeline.
RAID-009 | P003 | Issue | MI Pack delayed by JIRA API rate limit failure | Process | Medium |  | Amber | Ariful Haque | 2026-04-18 | 2026-04-25 | 2026-04-22 | Resolved | 4 | 0 | 0 | Switched to Azure DevOps OData feed. Added 2-hour production buffer.
RAID-010 | P003 | Risk | Power BI Premium licence cost not in baseline | Financial | Medium | High | Amber | Ariful Haque | 2026-03-15 | 2026-05-10 |  | Open | 44 | 12000 | 0 | Confirmed 12 licences needed. Change request raised to finance.
RAID-011 | P004 | Issue | Business case rejected — ROI assumptions challenged | Financial | Critical |  | Red | James Patel | 2026-04-01 | 2026-04-28 |  | In Progress | 28 | 0 | 28 | Revised ROI model in progress. CFO review scheduled 28 April.
RAID-012 | P004 | Risk | Smart Meter supplier API breaking changes in Q3 | Technical | High | Medium | Amber | Dev Team B | 2026-03-10 | 2026-05-15 |  | Open | 49 | 15000 | 21 | Build version-agnostic wrapper. Subscribe to API changelog alerts.
RAID-013 | P005 | Risk | Supplier unable to remediate 2 security controls | Compliance | High | Medium | Amber | Nina Sharma | 2026-03-01 | 2026-06-15 |  | Open | 59 | 20000 | 0 | Identify alternative compensating controls. Engage legal on contract breach.
RAID-014 | P008 | Issue | SAP integration complexity — undiscovered dependencies | Technical | Critical |  | Red | David Kim | 2026-02-15 | 2026-04-21 |  | In Progress | 73 | 68000 | 21 | Additional discovery sprint approved. Change request for revised timeline.
RAID-015 | P008 | Risk | Go-live conflicts with finance period-end close | Schedule | High | High | Red | David Kim | 2026-03-01 | 2026-05-31 |  | Open | 59 | 0 | 21 | Finance blackout 1-21 July. Revised go-live target 21 July minimum.

## DIM_Date
DateKey | FullDate | Year | Quarter | QuarterName | Month | MonthName | MonthShort | WeekNumber | DayOfWeek | DayName | IsWeekend | FiscalYear | FiscalQuarter | Period
20251001 | 2025-10-01 | 2025 | 4 | Q4 | 10 | October | Oct | 40 | 3 | Wednesday | No | FY2026 | FQ3 | 2025-10
20251002 | 2025-10-02 | 2025 | 4 | Q4 | 10 | October | Oct | 40 | 4 | Thursday | No | FY2026 | FQ3 | 2025-10
20251003 | 2025-10-03 | 2025 | 4 | Q4 | 10 | October | Oct | 40 | 5 | Friday | No | FY2026 | FQ3 | 2025-10
20251004 | 2025-10-04 | 2025 | 4 | Q4 | 10 | October | Oct | 40 | 6 | Saturday | Yes | FY2026 | FQ3 | 2025-10
20251005 | 2025-10-05 | 2025 | 4 | Q4 | 10 | October | Oct | 40 | 7 | Sunday | Yes | FY2026 | FQ3 | 2025-10
20251006 | 2025-10-06 | 2025 | 4 | Q4 | 10 | October | Oct | 41 | 1 | Monday | No | FY2026 | FQ3 | 2025-10
20251007 | 2025-10-07 | 2025 | 4 | Q4 | 10 | October | Oct | 41 | 2 | Tuesday | No | FY2026 | FQ3 | 2025-10
20251008 | 2025-10-08 | 2025 | 4 | Q4 | 10 | October | Oct | 41 | 3 | Wednesday | No | FY2026 | FQ3 | 2025-10
20251009 | 2025-10-09 | 2025 | 4 | Q4 | 10 | October | Oct | 41 | 4 | Thursday | No | FY2026 | FQ3 | 2025-10
20251010 | 2025-10-10 | 2025 | 4 | Q4 | 10 | October | Oct | 41 | 5 | Friday | No | FY2026 | FQ3 | 2025-10
20251011 | 2025-10-11 | 2025 | 4 | Q4 | 10 | October | Oct | 41 | 6 | Saturday | Yes | FY2026 | FQ3 | 2025-10
20251012 | 2025-10-12 | 2025 | 4 | Q4 | 10 | October | Oct | 41 | 7 | Sunday | Yes | FY2026 | FQ3 | 2025-10
20251013 | 2025-10-13 | 2025 | 4 | Q4 | 10 | October | Oct | 42 | 1 | Monday | No | FY2026 | FQ3 | 2025-10
20251014 | 2025-10-14 | 2025 | 4 | Q4 | 10 | October | Oct | 42 | 2 | Tuesday | No | FY2026 | FQ3 | 2025-10
20251015 | 2025-10-15 | 2025 | 4 | Q4 | 10 | October | Oct | 42 | 3 | Wednesday | No | FY2026 | FQ3 | 2025-10
20251016 | 2025-10-16 | 2025 | 4 | Q4 | 10 | October | Oct | 42 | 4 | Thursday | No | FY2026 | FQ3 | 2025-10
20251017 | 2025-10-17 | 2025 | 4 | Q4 | 10 | October | Oct | 42 | 5 | Friday | No | FY2026 | FQ3 | 2025-10
20251018 | 2025-10-18 | 2025 | 4 | Q4 | 10 | October | Oct | 42 | 6 | Saturday | Yes | FY2026 | FQ3 | 2025-10
20251019 | 2025-10-19 | 2025 | 4 | Q4 | 10 | October | Oct | 42 | 7 | Sunday | Yes | FY2026 | FQ3 | 2025-10
20251020 | 2025-10-20 | 2025 | 4 | Q4 | 10 | October | Oct | 43 | 1 | Monday | No | FY2026 | FQ3 | 2025-10
20251021 | 2025-10-21 | 2025 | 4 | Q4 | 10 | October | Oct | 43 | 2 | Tuesday | No | FY2026 | FQ3 | 2025-10
20251022 | 2025-10-22 | 2025 | 4 | Q4 | 10 | October | Oct | 43 | 3 | Wednesday | No | FY2026 | FQ3 | 2025-10
20251023 | 2025-10-23 | 2025 | 4 | Q4 | 10 | October | Oct | 43 | 4 | Thursday | No | FY2026 | FQ3 | 2025-10
20251024 | 2025-10-24 | 2025 | 4 | Q4 | 10 | October | Oct | 43 | 5 | Friday | No | FY2026 | FQ3 | 2025-10
20251025 | 2025-10-25 | 2025 | 4 | Q4 | 10 | October | Oct | 43 | 6 | Saturday | Yes | FY2026 | FQ3 | 2025-10
20251026 | 2025-10-26 | 2025 | 4 | Q4 | 10 | October | Oct | 43 | 7 | Sunday | Yes | FY2026 | FQ3 | 2025-10
20251027 | 2025-10-27 | 2025 | 4 | Q4 | 10 | October | Oct | 44 | 1 | Monday | No | FY2026 | FQ3 | 2025-10
20251028 | 2025-10-28 | 2025 | 4 | Q4 | 10 | October | Oct | 44 | 2 | Tuesday | No | FY2026 | FQ3 | 2025-10
20251029 | 2025-10-29 | 2025 | 4 | Q4 | 10 | October | Oct | 44 | 3 | Wednesday | No | FY2026 | FQ3 | 2025-10
20251030 | 2025-10-30 | 2025 | 4 | Q4 | 10 | October | Oct | 44 | 4 | Thursday | No | FY2026 | FQ3 | 2025-10
20251031 | 2025-10-31 | 2025 | 4 | Q4 | 10 | October | Oct | 44 | 5 | Friday | No | FY2026 | FQ3 | 2025-10
20251101 | 2025-11-01 | 2025 | 4 | Q4 | 11 | November | Nov | 44 | 6 | Saturday | Yes | FY2026 | FQ3 | 2025-11
20251102 | 2025-11-02 | 2025 | 4 | Q4 | 11 | November | Nov | 44 | 7 | Sunday | Yes | FY2026 | FQ3 | 2025-11
20251103 | 2025-11-03 | 2025 | 4 | Q4 | 11 | November | Nov | 45 | 1 | Monday | No | FY2026 | FQ3 | 2025-11
20251104 | 2025-11-04 | 2025 | 4 | Q4 | 11 | November | Nov | 45 | 2 | Tuesday | No | FY2026 | FQ3 | 2025-11
20251105 | 2025-11-05 | 2025 | 4 | Q4 | 11 | November | Nov | 45 | 3 | Wednesday | No | FY2026 | FQ3 | 2025-11
20251106 | 2025-11-06 | 2025 | 4 | Q4 | 11 | November | Nov | 45 | 4 | Thursday | No | FY2026 | FQ3 | 2025-11
20251107 | 2025-11-07 | 2025 | 4 | Q4 | 11 | November | Nov | 45 | 5 | Friday | No | FY2026 | FQ3 | 2025-11
20251108 | 2025-11-08 | 2025 | 4 | Q4 | 11 | November | Nov | 45 | 6 | Saturday | Yes | FY2026 | FQ3 | 2025-11
20251109 | 2025-11-09 | 2025 | 4 | Q4 | 11 | November | Nov | 45 | 7 | Sunday | Yes | FY2026 | FQ3 | 2025-11
20251110 | 2025-11-10 | 2025 | 4 | Q4 | 11 | November | Nov | 46 | 1 | Monday | No | FY2026 | FQ3 | 2025-11
20251111 | 2025-11-11 | 2025 | 4 | Q4 | 11 | November | Nov | 46 | 2 | Tuesday | No | FY2026 | FQ3 | 2025-11
20251112 | 2025-11-12 | 2025 | 4 | Q4 | 11 | November | Nov | 46 | 3 | Wednesday | No | FY2026 | FQ3 | 2025-11
20251113 | 2025-11-13 | 2025 | 4 | Q4 | 11 | November | Nov | 46 | 4 | Thursday | No | FY2026 | FQ3 | 2025-11
20251114 | 2025-11-14 | 2025 | 4 | Q4 | 11 | November | Nov | 46 | 5 | Friday | No | FY2026 | FQ3 | 2025-11
20251115 | 2025-11-15 | 2025 | 4 | Q4 | 11 | November | Nov | 46 | 6 | Saturday | Yes | FY2026 | FQ3 | 2025-11
20251116 | 2025-11-16 | 2025 | 4 | Q4 | 11 | November | Nov | 46 | 7 | Sunday | Yes | FY2026 | FQ3 | 2025-11
20251117 | 2025-11-17 | 2025 | 4 | Q4 | 11 | November | Nov | 47 | 1 | Monday | No | FY2026 | FQ3 | 2025-11
20251118 | 2025-11-18 | 2025 | 4 | Q4 | 11 | November | Nov | 47 | 2 | Tuesday | No | FY2026 | FQ3 | 2025-11
20251119 | 2025-11-19 | 2025 | 4 | Q4 | 11 | November | Nov | 47 | 3 | Wednesday | No | FY2026 | FQ3 | 2025-11
20251120 | 2025-11-20 | 2025 | 4 | Q4 | 11 | November | Nov | 47 | 4 | Thursday | No | FY2026 | FQ3 | 2025-11
20251121 | 2025-11-21 | 2025 | 4 | Q4 | 11 | November | Nov | 47 | 5 | Friday | No | FY2026 | FQ3 | 2025-11
20251122 | 2025-11-22 | 2025 | 4 | Q4 | 11 | November | Nov | 47 | 6 | Saturday | Yes | FY2026 | FQ3 | 2025-11
20251123 | 2025-11-23 | 2025 | 4 | Q4 | 11 | November | Nov | 47 | 7 | Sunday | Yes | FY2026 | FQ3 | 2025-11
20251124 | 2025-11-24 | 2025 | 4 | Q4 | 11 | November | Nov | 48 | 1 | Monday | No | FY2026 | FQ3 | 2025-11
20251125 | 2025-11-25 | 2025 | 4 | Q4 | 11 | November | Nov | 48 | 2 | Tuesday | No | FY2026 | FQ3 | 2025-11
20251126 | 2025-11-26 | 2025 | 4 | Q4 | 11 | November | Nov | 48 | 3 | Wednesday | No | FY2026 | FQ3 | 2025-11
20251127 | 2025-11-27 | 2025 | 4 | Q4 | 11 | November | Nov | 48 | 4 | Thursday | No | FY2026 | FQ3 | 2025-11
20251128 | 2025-11-28 | 2025 | 4 | Q4 | 11 | November | Nov | 48 | 5 | Friday | No | FY2026 | FQ3 | 2025-11
20251129 | 2025-11-29 | 2025 | 4 | Q4 | 11 | November | Nov | 48 | 6 | Saturday | Yes | FY2026 | FQ3 | 2025-11
20251130 | 2025-11-30 | 2025 | 4 | Q4 | 11 | November | Nov | 48 | 7 | Sunday | Yes | FY2026 | FQ3 | 2025-11
20251201 | 2025-12-01 | 2025 | 4 | Q4 | 12 | December | Dec | 49 | 1 | Monday | No | FY2026 | FQ3 | 2025-12
20251202 | 2025-12-02 | 2025 | 4 | Q4 | 12 | December | Dec | 49 | 2 | Tuesday | No | FY2026 | FQ3 | 2025-12
20251203 | 2025-12-03 | 2025 | 4 | Q4 | 12 | December | Dec | 49 | 3 | Wednesday | No | FY2026 | FQ3 | 2025-12
20251204 | 2025-12-04 | 2025 | 4 | Q4 | 12 | December | Dec | 49 | 4 | Thursday | No | FY2026 | FQ3 | 2025-12
20251205 | 2025-12-05 | 2025 | 4 | Q4 | 12 | December | Dec | 49 | 5 | Friday | No | FY2026 | FQ3 | 2025-12
20251206 | 2025-12-06 | 2025 | 4 | Q4 | 12 | December | Dec | 49 | 6 | Saturday | Yes | FY2026 | FQ3 | 2025-12
20251207 | 2025-12-07 | 2025 | 4 | Q4 | 12 | December | Dec | 49 | 7 | Sunday | Yes | FY2026 | FQ3 | 2025-12
20251208 | 2025-12-08 | 2025 | 4 | Q4 | 12 | December | Dec | 50 | 1 | Monday | No | FY2026 | FQ3 | 2025-12
20251209 | 2025-12-09 | 2025 | 4 | Q4 | 12 | December | Dec | 50 | 2 | Tuesday | No | FY2026 | FQ3 | 2025-12
20251210 | 2025-12-10 | 2025 | 4 | Q4 | 12 | December | Dec | 50 | 3 | Wednesday | No | FY2026 | FQ3 | 2025-12
20251211 | 2025-12-11 | 2025 | 4 | Q4 | 12 | December | Dec | 50 | 4 | Thursday | No | FY2026 | FQ3 | 2025-12
20251212 | 2025-12-12 | 2025 | 4 | Q4 | 12 | December | Dec | 50 | 5 | Friday | No | FY2026 | FQ3 | 2025-12
20251213 | 2025-12-13 | 2025 | 4 | Q4 | 12 | December | Dec | 50 | 6 | Saturday | Yes | FY2026 | FQ3 | 2025-12
20251214 | 2025-12-14 | 2025 | 4 | Q4 | 12 | December | Dec | 50 | 7 | Sunday | Yes | FY2026 | FQ3 | 2025-12
20251215 | 2025-12-15 | 2025 | 4 | Q4 | 12 | December | Dec | 51 | 1 | Monday | No | FY2026 | FQ3 | 2025-12
20251216 | 2025-12-16 | 2025 | 4 | Q4 | 12 | December | Dec | 51 | 2 | Tuesday | No | FY2026 | FQ3 | 2025-12
20251217 | 2025-12-17 | 2025 | 4 | Q4 | 12 | December | Dec | 51 | 3 | Wednesday | No | FY2026 | FQ3 | 2025-12
20251218 | 2025-12-18 | 2025 | 4 | Q4 | 12 | December | Dec | 51 | 4 | Thursday | No | FY2026 | FQ3 | 2025-12
20251219 | 2025-12-19 | 2025 | 4 | Q4 | 12 | December | Dec | 51 | 5 | Friday | No | FY2026 | FQ3 | 2025-12
20251220 | 2025-12-20 | 2025 | 4 | Q4 | 12 | December | Dec | 51 | 6 | Saturday | Yes | FY2026 | FQ3 | 2025-12
20251221 | 2025-12-21 | 2025 | 4 | Q4 | 12 | December | Dec | 51 | 7 | Sunday | Yes | FY2026 | FQ3 | 2025-12
20251222 | 2025-12-22 | 2025 | 4 | Q4 | 12 | December | Dec | 52 | 1 | Monday | No | FY2026 | FQ3 | 2025-12
20251223 | 2025-12-23 | 2025 | 4 | Q4 | 12 | December | Dec | 52 | 2 | Tuesday | No | FY2026 | FQ3 | 2025-12
20251224 | 2025-12-24 | 2025 | 4 | Q4 | 12 | December | Dec | 52 | 3 | Wednesday | No | FY2026 | FQ3 | 2025-12
20251225 | 2025-12-25 | 2025 | 4 | Q4 | 12 | December | Dec | 52 | 4 | Thursday | No | FY2026 | FQ3 | 2025-12
20251226 | 2025-12-26 | 2025 | 4 | Q4 | 12 | December | Dec | 52 | 5 | Friday | No | FY2026 | FQ3 | 2025-12
20251227 | 2025-12-27 | 2025 | 4 | Q4 | 12 | December | Dec | 52 | 6 | Saturday | Yes | FY2026 | FQ3 | 2025-12
20251228 | 2025-12-28 | 2025 | 4 | Q4 | 12 | December | Dec | 52 | 7 | Sunday | Yes | FY2026 | FQ3 | 2025-12
20251229 | 2025-12-29 | 2025 | 4 | Q4 | 12 | December | Dec | 1 | 1 | Monday | No | FY2026 | FQ3 | 2025-12
20251230 | 2025-12-30 | 2025 | 4 | Q4 | 12 | December | Dec | 1 | 2 | Tuesday | No | FY2026 | FQ3 | 2025-12
20251231 | 2025-12-31 | 2025 | 4 | Q4 | 12 | December | Dec | 1 | 3 | Wednesday | No | FY2026 | FQ3 | 2025-12
20260101 | 2026-01-01 | 2026 | 1 | Q1 | 1 | January | Jan | 1 | 4 | Thursday | No | FY2026 | FQ4 | 2026-01
20260102 | 2026-01-02 | 2026 | 1 | Q1 | 1 | January | Jan | 1 | 5 | Friday | No | FY2026 | FQ4 | 2026-01
20260103 | 2026-01-03 | 2026 | 1 | Q1 | 1 | January | Jan | 1 | 6 | Saturday | Yes | FY2026 | FQ4 | 2026-01
20260104 | 2026-01-04 | 2026 | 1 | Q1 | 1 | January | Jan | 1 | 7 | Sunday | Yes | FY2026 | FQ4 | 2026-01
20260105 | 2026-01-05 | 2026 | 1 | Q1 | 1 | January | Jan | 2 | 1 | Monday | No | FY2026 | FQ4 | 2026-01
20260106 | 2026-01-06 | 2026 | 1 | Q1 | 1 | January | Jan | 2 | 2 | Tuesday | No | FY2026 | FQ4 | 2026-01
20260107 | 2026-01-07 | 2026 | 1 | Q1 | 1 | January | Jan | 2 | 3 | Wednesday | No | FY2026 | FQ4 | 2026-01
20260108 | 2026-01-08 | 2026 | 1 | Q1 | 1 | January | Jan | 2 | 4 | Thursday | No | FY2026 | FQ4 | 2026-01
20260109 | 2026-01-09 | 2026 | 1 | Q1 | 1 | January | Jan | 2 | 5 | Friday | No | FY2026 | FQ4 | 2026-01
20260110 | 2026-01-10 | 2026 | 1 | Q1 | 1 | January | Jan | 2 | 6 | Saturday | Yes | FY2026 | FQ4 | 2026-01
20260111 | 2026-01-11 | 2026 | 1 | Q1 | 1 | January | Jan | 2 | 7 | Sunday | Yes | FY2026 | FQ4 | 2026-01
20260112 | 2026-01-12 | 2026 | 1 | Q1 | 1 | January | Jan | 3 | 1 | Monday | No | FY2026 | FQ4 | 2026-01
20260113 | 2026-01-13 | 2026 | 1 | Q1 | 1 | January | Jan | 3 | 2 | Tuesday | No | FY2026 | FQ4 | 2026-01
20260114 | 2026-01-14 | 2026 | 1 | Q1 | 1 | January | Jan | 3 | 3 | Wednesday | No | FY2026 | FQ4 | 2026-01
20260115 | 2026-01-15 | 2026 | 1 | Q1 | 1 | January | Jan | 3 | 4 | Thursday | No | FY2026 | FQ4 | 2026-01
20260116 | 2026-01-16 | 2026 | 1 | Q1 | 1 | January | Jan | 3 | 5 | Friday | No | FY2026 | FQ4 | 2026-01
20260117 | 2026-01-17 | 2026 | 1 | Q1 | 1 | January | Jan | 3 | 6 | Saturday | Yes | FY2026 | FQ4 | 2026-01
20260118 | 2026-01-18 | 2026 | 1 | Q1 | 1 | January | Jan | 3 | 7 | Sunday | Yes | FY2026 | FQ4 | 2026-01
20260119 | 2026-01-19 | 2026 | 1 | Q1 | 1 | January | Jan | 4 | 1 | Monday | No | FY2026 | FQ4 | 2026-01
20260120 | 2026-01-20 | 2026 | 1 | Q1 | 1 | January | Jan | 4 | 2 | Tuesday | No | FY2026 | FQ4 | 2026-01
20260121 | 2026-01-21 | 2026 | 1 | Q1 | 1 | January | Jan | 4 | 3 | Wednesday | No | FY2026 | FQ4 | 2026-01
20260122 | 2026-01-22 | 2026 | 1 | Q1 | 1 | January | Jan | 4 | 4 | Thursday | No | FY2026 | FQ4 | 2026-01
20260123 | 2026-01-23 | 2026 | 1 | Q1 | 1 | January | Jan | 4 | 5 | Friday | No | FY2026 | FQ4 | 2026-01
20260124 | 2026-01-24 | 2026 | 1 | Q1 | 1 | January | Jan | 4 | 6 | Saturday | Yes | FY2026 | FQ4 | 2026-01
20260125 | 2026-01-25 | 2026 | 1 | Q1 | 1 | January | Jan | 4 | 7 | Sunday | Yes | FY2026 | FQ4 | 2026-01
20260126 | 2026-01-26 | 2026 | 1 | Q1 | 1 | January | Jan | 5 | 1 | Monday | No | FY2026 | FQ4 | 2026-01
20260127 | 2026-01-27 | 2026 | 1 | Q1 | 1 | January | Jan | 5 | 2 | Tuesday | No | FY2026 | FQ4 | 2026-01
20260128 | 2026-01-28 | 2026 | 1 | Q1 | 1 | January | Jan | 5 | 3 | Wednesday | No | FY2026 | FQ4 | 2026-01
20260129 | 2026-01-29 | 2026 | 1 | Q1 | 1 | January | Jan | 5 | 4 | Thursday | No | FY2026 | FQ4 | 2026-01
20260130 | 2026-01-30 | 2026 | 1 | Q1 | 1 | January | Jan | 5 | 5 | Friday | No | FY2026 | FQ4 | 2026-01
20260131 | 2026-01-31 | 2026 | 1 | Q1 | 1 | January | Jan | 5 | 6 | Saturday | Yes | FY2026 | FQ4 | 2026-01
20260201 | 2026-02-01 | 2026 | 1 | Q1 | 2 | February | Feb | 5 | 7 | Sunday | Yes | FY2026 | FQ4 | 2026-02
20260202 | 2026-02-02 | 2026 | 1 | Q1 | 2 | February | Feb | 6 | 1 | Monday | No | FY2026 | FQ4 | 2026-02
20260203 | 2026-02-03 | 2026 | 1 | Q1 | 2 | February | Feb | 6 | 2 | Tuesday | No | FY2026 | FQ4 | 2026-02
20260204 | 2026-02-04 | 2026 | 1 | Q1 | 2 | February | Feb | 6 | 3 | Wednesday | No | FY2026 | FQ4 | 2026-02
20260205 | 2026-02-05 | 2026 | 1 | Q1 | 2 | February | Feb | 6 | 4 | Thursday | No | FY2026 | FQ4 | 2026-02
20260206 | 2026-02-06 | 2026 | 1 | Q1 | 2 | February | Feb | 6 | 5 | Friday | No | FY2026 | FQ4 | 2026-02
20260207 | 2026-02-07 | 2026 | 1 | Q1 | 2 | February | Feb | 6 | 6 | Saturday | Yes | FY2026 | FQ4 | 2026-02
20260208 | 2026-02-08 | 2026 | 1 | Q1 | 2 | February | Feb | 6 | 7 | Sunday | Yes | FY2026 | FQ4 | 2026-02
20260209 | 2026-02-09 | 2026 | 1 | Q1 | 2 | February | Feb | 7 | 1 | Monday | No | FY2026 | FQ4 | 2026-02
20260210 | 2026-02-10 | 2026 | 1 | Q1 | 2 | February | Feb | 7 | 2 | Tuesday | No | FY2026 | FQ4 | 2026-02
20260211 | 2026-02-11 | 2026 | 1 | Q1 | 2 | February | Feb | 7 | 3 | Wednesday | No | FY2026 | FQ4 | 2026-02
20260212 | 2026-02-12 | 2026 | 1 | Q1 | 2 | February | Feb | 7 | 4 | Thursday | No | FY2026 | FQ4 | 2026-02
20260213 | 2026-02-13 | 2026 | 1 | Q1 | 2 | February | Feb | 7 | 5 | Friday | No | FY2026 | FQ4 | 2026-02
20260214 | 2026-02-14 | 2026 | 1 | Q1 | 2 | February | Feb | 7 | 6 | Saturday | Yes | FY2026 | FQ4 | 2026-02
20260215 | 2026-02-15 | 2026 | 1 | Q1 | 2 | February | Feb | 7 | 7 | Sunday | Yes | FY2026 | FQ4 | 2026-02
20260216 | 2026-02-16 | 2026 | 1 | Q1 | 2 | February | Feb | 8 | 1 | Monday | No | FY2026 | FQ4 | 2026-02
20260217 | 2026-02-17 | 2026 | 1 | Q1 | 2 | February | Feb | 8 | 2 | Tuesday | No | FY2026 | FQ4 | 2026-02
20260218 | 2026-02-18 | 2026 | 1 | Q1 | 2 | February | Feb | 8 | 3 | Wednesday | No | FY2026 | FQ4 | 2026-02
20260219 | 2026-02-19 | 2026 | 1 | Q1 | 2 | February | Feb | 8 | 4 | Thursday | No | FY2026 | FQ4 | 2026-02
20260220 | 2026-02-20 | 2026 | 1 | Q1 | 2 | February | Feb | 8 | 5 | Friday | No | FY2026 | FQ4 | 2026-02
20260221 | 2026-02-21 | 2026 | 1 | Q1 | 2 | February | Feb | 8 | 6 | Saturday | Yes | FY2026 | FQ4 | 2026-02
20260222 | 2026-02-22 | 2026 | 1 | Q1 | 2 | February | Feb | 8 | 7 | Sunday | Yes | FY2026 | FQ4 | 2026-02
20260223 | 2026-02-23 | 2026 | 1 | Q1 | 2 | February | Feb | 9 | 1 | Monday | No | FY2026 | FQ4 | 2026-02
20260224 | 2026-02-24 | 2026 | 1 | Q1 | 2 | February | Feb | 9 | 2 | Tuesday | No | FY2026 | FQ4 | 2026-02
20260225 | 2026-02-25 | 2026 | 1 | Q1 | 2 | February | Feb | 9 | 3 | Wednesday | No | FY2026 | FQ4 | 2026-02
20260226 | 2026-02-26 | 2026 | 1 | Q1 | 2 | February | Feb | 9 | 4 | Thursday | No | FY2026 | FQ4 | 2026-02
20260227 | 2026-02-27 | 2026 | 1 | Q1 | 2 | February | Feb | 9 | 5 | Friday | No | FY2026 | FQ4 | 2026-02
20260228 | 2026-02-28 | 2026 | 1 | Q1 | 2 | February | Feb | 9 | 6 | Saturday | Yes | FY2026 | FQ4 | 2026-02
20260301 | 2026-03-01 | 2026 | 1 | Q1 | 3 | March | Mar | 9 | 7 | Sunday | Yes | FY2026 | FQ4 | 2026-03
20260302 | 2026-03-02 | 2026 | 1 | Q1 | 3 | March | Mar | 10 | 1 | Monday | No | FY2026 | FQ4 | 2026-03
20260303 | 2026-03-03 | 2026 | 1 | Q1 | 3 | March | Mar | 10 | 2 | Tuesday | No | FY2026 | FQ4 | 2026-03
20260304 | 2026-03-04 | 2026 | 1 | Q1 | 3 | March | Mar | 10 | 3 | Wednesday | No | FY2026 | FQ4 | 2026-03
20260305 | 2026-03-05 | 2026 | 1 | Q1 | 3 | March | Mar | 10 | 4 | Thursday | No | FY2026 | FQ4 | 2026-03
20260306 | 2026-03-06 | 2026 | 1 | Q1 | 3 | March | Mar | 10 | 5 | Friday | No | FY2026 | FQ4 | 2026-03
20260307 | 2026-03-07 | 2026 | 1 | Q1 | 3 | March | Mar | 10 | 6 | Saturday | Yes | FY2026 | FQ4 | 2026-03
20260308 | 2026-03-08 | 2026 | 1 | Q1 | 3 | March | Mar | 10 | 7 | Sunday | Yes | FY2026 | FQ4 | 2026-03
20260309 | 2026-03-09 | 2026 | 1 | Q1 | 3 | March | Mar | 11 | 1 | Monday | No | FY2026 | FQ4 | 2026-03
20260310 | 2026-03-10 | 2026 | 1 | Q1 | 3 | March | Mar | 11 | 2 | Tuesday | No | FY2026 | FQ4 | 2026-03
20260311 | 2026-03-11 | 2026 | 1 | Q1 | 3 | March | Mar | 11 | 3 | Wednesday | No | FY2026 | FQ4 | 2026-03
20260312 | 2026-03-12 | 2026 | 1 | Q1 | 3 | March | Mar | 11 | 4 | Thursday | No | FY2026 | FQ4 | 2026-03
20260313 | 2026-03-13 | 2026 | 1 | Q1 | 3 | March | Mar | 11 | 5 | Friday | No | FY2026 | FQ4 | 2026-03
20260314 | 2026-03-14 | 2026 | 1 | Q1 | 3 | March | Mar | 11 | 6 | Saturday | Yes | FY2026 | FQ4 | 2026-03
20260315 | 2026-03-15 | 2026 | 1 | Q1 | 3 | March | Mar | 11 | 7 | Sunday | Yes | FY2026 | FQ4 | 2026-03
20260316 | 2026-03-16 | 2026 | 1 | Q1 | 3 | March | Mar | 12 | 1 | Monday | No | FY2026 | FQ4 | 2026-03
20260317 | 2026-03-17 | 2026 | 1 | Q1 | 3 | March | Mar | 12 | 2 | Tuesday | No | FY2026 | FQ4 | 2026-03
20260318 | 2026-03-18 | 2026 | 1 | Q1 | 3 | March | Mar | 12 | 3 | Wednesday | No | FY2026 | FQ4 | 2026-03
20260319 | 2026-03-19 | 2026 | 1 | Q1 | 3 | March | Mar | 12 | 4 | Thursday | No | FY2026 | FQ4 | 2026-03
20260320 | 2026-03-20 | 2026 | 1 | Q1 | 3 | March | Mar | 12 | 5 | Friday | No | FY2026 | FQ4 | 2026-03
20260321 | 2026-03-21 | 2026 | 1 | Q1 | 3 | March | Mar | 12 | 6 | Saturday | Yes | FY2026 | FQ4 | 2026-03
20260322 | 2026-03-22 | 2026 | 1 | Q1 | 3 | March | Mar | 12 | 7 | Sunday | Yes | FY2026 | FQ4 | 2026-03
20260323 | 2026-03-23 | 2026 | 1 | Q1 | 3 | March | Mar | 13 | 1 | Monday | No | FY2026 | FQ4 | 2026-03
20260324 | 2026-03-24 | 2026 | 1 | Q1 | 3 | March | Mar | 13 | 2 | Tuesday | No | FY2026 | FQ4 | 2026-03
20260325 | 2026-03-25 | 2026 | 1 | Q1 | 3 | March | Mar | 13 | 3 | Wednesday | No | FY2026 | FQ4 | 2026-03
20260326 | 2026-03-26 | 2026 | 1 | Q1 | 3 | March | Mar | 13 | 4 | Thursday | No | FY2026 | FQ4 | 2026-03
20260327 | 2026-03-27 | 2026 | 1 | Q1 | 3 | March | Mar | 13 | 5 | Friday | No | FY2026 | FQ4 | 2026-03
20260328 | 2026-03-28 | 2026 | 1 | Q1 | 3 | March | Mar | 13 | 6 | Saturday | Yes | FY2026 | FQ4 | 2026-03
20260329 | 2026-03-29 | 2026 | 1 | Q1 | 3 | March | Mar | 13 | 7 | Sunday | Yes | FY2026 | FQ4 | 2026-03
20260330 | 2026-03-30 | 2026 | 1 | Q1 | 3 | March | Mar | 14 | 1 | Monday | No | FY2026 | FQ4 | 2026-03
20260331 | 2026-03-31 | 2026 | 1 | Q1 | 3 | March | Mar | 14 | 2 | Tuesday | No | FY2026 | FQ4 | 2026-03
20260401 | 2026-04-01 | 2026 | 2 | Q2 | 4 | April | Apr | 14 | 3 | Wednesday | No | FY2027 | FQ1 | 2026-04
20260402 | 2026-04-02 | 2026 | 2 | Q2 | 4 | April | Apr | 14 | 4 | Thursday | No | FY2027 | FQ1 | 2026-04
20260403 | 2026-04-03 | 2026 | 2 | Q2 | 4 | April | Apr | 14 | 5 | Friday | No | FY2027 | FQ1 | 2026-04
20260404 | 2026-04-04 | 2026 | 2 | Q2 | 4 | April | Apr | 14 | 6 | Saturday | Yes | FY2027 | FQ1 | 2026-04
20260405 | 2026-04-05 | 2026 | 2 | Q2 | 4 | April | Apr | 14 | 7 | Sunday | Yes | FY2027 | FQ1 | 2026-04
20260406 | 2026-04-06 | 2026 | 2 | Q2 | 4 | April | Apr | 15 | 1 | Monday | No | FY2027 | FQ1 | 2026-04
20260407 | 2026-04-07 | 2026 | 2 | Q2 | 4 | April | Apr | 15 | 2 | Tuesday | No | FY2027 | FQ1 | 2026-04
20260408 | 2026-04-08 | 2026 | 2 | Q2 | 4 | April | Apr | 15 | 3 | Wednesday | No | FY2027 | FQ1 | 2026-04
20260409 | 2026-04-09 | 2026 | 2 | Q2 | 4 | April | Apr | 15 | 4 | Thursday | No | FY2027 | FQ1 | 2026-04
20260410 | 2026-04-10 | 2026 | 2 | Q2 | 4 | April | Apr | 15 | 5 | Friday | No | FY2027 | FQ1 | 2026-04
20260411 | 2026-04-11 | 2026 | 2 | Q2 | 4 | April | Apr | 15 | 6 | Saturday | Yes | FY2027 | FQ1 | 2026-04
20260412 | 2026-04-12 | 2026 | 2 | Q2 | 4 | April | Apr | 15 | 7 | Sunday | Yes | FY2027 | FQ1 | 2026-04
20260413 | 2026-04-13 | 2026 | 2 | Q2 | 4 | April | Apr | 16 | 1 | Monday | No | FY2027 | FQ1 | 2026-04
20260414 | 2026-04-14 | 2026 | 2 | Q2 | 4 | April | Apr | 16 | 2 | Tuesday | No | FY2027 | FQ1 | 2026-04
20260415 | 2026-04-15 | 2026 | 2 | Q2 | 4 | April | Apr | 16 | 3 | Wednesday | No | FY2027 | FQ1 | 2026-04
20260416 | 2026-04-16 | 2026 | 2 | Q2 | 4 | April | Apr | 16 | 4 | Thursday | No | FY2027 | FQ1 | 2026-04
20260417 | 2026-04-17 | 2026 | 2 | Q2 | 4 | April | Apr | 16 | 5 | Friday | No | FY2027 | FQ1 | 2026-04
20260418 | 2026-04-18 | 2026 | 2 | Q2 | 4 | April | Apr | 16 | 6 | Saturday | Yes | FY2027 | FQ1 | 2026-04
20260419 | 2026-04-19 | 2026 | 2 | Q2 | 4 | April | Apr | 16 | 7 | Sunday | Yes | FY2027 | FQ1 | 2026-04
20260420 | 2026-04-20 | 2026 | 2 | Q2 | 4 | April | Apr | 17 | 1 | Monday | No | FY2027 | FQ1 | 2026-04
20260421 | 2026-04-21 | 2026 | 2 | Q2 | 4 | April | Apr | 17 | 2 | Tuesday | No | FY2027 | FQ1 | 2026-04
20260422 | 2026-04-22 | 2026 | 2 | Q2 | 4 | April | Apr | 17 | 3 | Wednesday | No | FY2027 | FQ1 | 2026-04
20260423 | 2026-04-23 | 2026 | 2 | Q2 | 4 | April | Apr | 17 | 4 | Thursday | No | FY2027 | FQ1 | 2026-04
20260424 | 2026-04-24 | 2026 | 2 | Q2 | 4 | April | Apr | 17 | 5 | Friday | No | FY2027 | FQ1 | 2026-04
20260425 | 2026-04-25 | 2026 | 2 | Q2 | 4 | April | Apr | 17 | 6 | Saturday | Yes | FY2027 | FQ1 | 2026-04
20260426 | 2026-04-26 | 2026 | 2 | Q2 | 4 | April | Apr | 17 | 7 | Sunday | Yes | FY2027 | FQ1 | 2026-04
20260427 | 2026-04-27 | 2026 | 2 | Q2 | 4 | April | Apr | 18 | 1 | Monday | No | FY2027 | FQ1 | 2026-04
20260428 | 2026-04-28 | 2026 | 2 | Q2 | 4 | April | Apr | 18 | 2 | Tuesday | No | FY2027 | FQ1 | 2026-04
20260429 | 2026-04-29 | 2026 | 2 | Q2 | 4 | April | Apr | 18 | 3 | Wednesday | No | FY2027 | FQ1 | 2026-04
20260430 | 2026-04-30 | 2026 | 2 | Q2 | 4 | April | Apr | 18 | 4 | Thursday | No | FY2027 | FQ1 | 2026-04
20260501 | 2026-05-01 | 2026 | 2 | Q2 | 5 | May | May | 18 | 5 | Friday | No | FY2027 | FQ1 | 2026-05
20260502 | 2026-05-02 | 2026 | 2 | Q2 | 5 | May | May | 18 | 6 | Saturday | Yes | FY2027 | FQ1 | 2026-05
20260503 | 2026-05-03 | 2026 | 2 | Q2 | 5 | May | May | 18 | 7 | Sunday | Yes | FY2027 | FQ1 | 2026-05
20260504 | 2026-05-04 | 2026 | 2 | Q2 | 5 | May | May | 19 | 1 | Monday | No | FY2027 | FQ1 | 2026-05
20260505 | 2026-05-05 | 2026 | 2 | Q2 | 5 | May | May | 19 | 2 | Tuesday | No | FY2027 | FQ1 | 2026-05
20260506 | 2026-05-06 | 2026 | 2 | Q2 | 5 | May | May | 19 | 3 | Wednesday | No | FY2027 | FQ1 | 2026-05
20260507 | 2026-05-07 | 2026 | 2 | Q2 | 5 | May | May | 19 | 4 | Thursday | No | FY2027 | FQ1 | 2026-05
20260508 | 2026-05-08 | 2026 | 2 | Q2 | 5 | May | May | 19 | 5 | Friday | No | FY2027 | FQ1 | 2026-05
20260509 | 2026-05-09 | 2026 | 2 | Q2 | 5 | May | May | 19 | 6 | Saturday | Yes | FY2027 | FQ1 | 2026-05
20260510 | 2026-05-10 | 2026 | 2 | Q2 | 5 | May | May | 19 | 7 | Sunday | Yes | FY2027 | FQ1 | 2026-05
20260511 | 2026-05-11 | 2026 | 2 | Q2 | 5 | May | May | 20 | 1 | Monday | No | FY2027 | FQ1 | 2026-05
20260512 | 2026-05-12 | 2026 | 2 | Q2 | 5 | May | May | 20 | 2 | Tuesday | No | FY2027 | FQ1 | 2026-05
20260513 | 2026-05-13 | 2026 | 2 | Q2 | 5 | May | May | 20 | 3 | Wednesday | No | FY2027 | FQ1 | 2026-05
20260514 | 2026-05-14 | 2026 | 2 | Q2 | 5 | May | May | 20 | 4 | Thursday | No | FY2027 | FQ1 | 2026-05
20260515 | 2026-05-15 | 2026 | 2 | Q2 | 5 | May | May | 20 | 5 | Friday | No | FY2027 | FQ1 | 2026-05
20260516 | 2026-05-16 | 2026 | 2 | Q2 | 5 | May | May | 20 | 6 | Saturday | Yes | FY2027 | FQ1 | 2026-05
20260517 | 2026-05-17 | 2026 | 2 | Q2 | 5 | May | May | 20 | 7 | Sunday | Yes | FY2027 | FQ1 | 2026-05
20260518 | 2026-05-18 | 2026 | 2 | Q2 | 5 | May | May | 21 | 1 | Monday | No | FY2027 | FQ1 | 2026-05
20260519 | 2026-05-19 | 2026 | 2 | Q2 | 5 | May | May | 21 | 2 | Tuesday | No | FY2027 | FQ1 | 2026-05
20260520 | 2026-05-20 | 2026 | 2 | Q2 | 5 | May | May | 21 | 3 | Wednesday | No | FY2027 | FQ1 | 2026-05
20260521 | 2026-05-21 | 2026 | 2 | Q2 | 5 | May | May | 21 | 4 | Thursday | No | FY2027 | FQ1 | 2026-05
20260522 | 2026-05-22 | 2026 | 2 | Q2 | 5 | May | May | 21 | 5 | Friday | No | FY2027 | FQ1 | 2026-05
20260523 | 2026-05-23 | 2026 | 2 | Q2 | 5 | May | May | 21 | 6 | Saturday | Yes | FY2027 | FQ1 | 2026-05
20260524 | 2026-05-24 | 2026 | 2 | Q2 | 5 | May | May | 21 | 7 | Sunday | Yes | FY2027 | FQ1 | 2026-05
20260525 | 2026-05-25 | 2026 | 2 | Q2 | 5 | May | May | 22 | 1 | Monday | No | FY2027 | FQ1 | 2026-05
20260526 | 2026-05-26 | 2026 | 2 | Q2 | 5 | May | May | 22 | 2 | Tuesday | No | FY2027 | FQ1 | 2026-05
20260527 | 2026-05-27 | 2026 | 2 | Q2 | 5 | May | May | 22 | 3 | Wednesday | No | FY2027 | FQ1 | 2026-05
20260528 | 2026-05-28 | 2026 | 2 | Q2 | 5 | May | May | 22 | 4 | Thursday | No | FY2027 | FQ1 | 2026-05
20260529 | 2026-05-29 | 2026 | 2 | Q2 | 5 | May | May | 22 | 5 | Friday | No | FY2027 | FQ1 | 2026-05
20260530 | 2026-05-30 | 2026 | 2 | Q2 | 5 | May | May | 22 | 6 | Saturday | Yes | FY2027 | FQ1 | 2026-05
20260531 | 2026-05-31 | 2026 | 2 | Q2 | 5 | May | May | 22 | 7 | Sunday | Yes | FY2027 | FQ1 | 2026-05
20260601 | 2026-06-01 | 2026 | 2 | Q2 | 6 | June | Jun | 23 | 1 | Monday | No | FY2027 | FQ1 | 2026-06
20260602 | 2026-06-02 | 2026 | 2 | Q2 | 6 | June | Jun | 23 | 2 | Tuesday | No | FY2027 | FQ1 | 2026-06
20260603 | 2026-06-03 | 2026 | 2 | Q2 | 6 | June | Jun | 23 | 3 | Wednesday | No | FY2027 | FQ1 | 2026-06
20260604 | 2026-06-04 | 2026 | 2 | Q2 | 6 | June | Jun | 23 | 4 | Thursday | No | FY2027 | FQ1 | 2026-06
20260605 | 2026-06-05 | 2026 | 2 | Q2 | 6 | June | Jun | 23 | 5 | Friday | No | FY2027 | FQ1 | 2026-06
20260606 | 2026-06-06 | 2026 | 2 | Q2 | 6 | June | Jun | 23 | 6 | Saturday | Yes | FY2027 | FQ1 | 2026-06
20260607 | 2026-06-07 | 2026 | 2 | Q2 | 6 | June | Jun | 23 | 7 | Sunday | Yes | FY2027 | FQ1 | 2026-06
20260608 | 2026-06-08 | 2026 | 2 | Q2 | 6 | June | Jun | 24 | 1 | Monday | No | FY2027 | FQ1 | 2026-06
20260609 | 2026-06-09 | 2026 | 2 | Q2 | 6 | June | Jun | 24 | 2 | Tuesday | No | FY2027 | FQ1 | 2026-06
20260610 | 2026-06-10 | 2026 | 2 | Q2 | 6 | June | Jun | 24 | 3 | Wednesday | No | FY2027 | FQ1 | 2026-06
20260611 | 2026-06-11 | 2026 | 2 | Q2 | 6 | June | Jun | 24 | 4 | Thursday | No | FY2027 | FQ1 | 2026-06
20260612 | 2026-06-12 | 2026 | 2 | Q2 | 6 | June | Jun | 24 | 5 | Friday | No | FY2027 | FQ1 | 2026-06
20260613 | 2026-06-13 | 2026 | 2 | Q2 | 6 | June | Jun | 24 | 6 | Saturday | Yes | FY2027 | FQ1 | 2026-06
20260614 | 2026-06-14 | 2026 | 2 | Q2 | 6 | June | Jun | 24 | 7 | Sunday | Yes | FY2027 | FQ1 | 2026-06
20260615 | 2026-06-15 | 2026 | 2 | Q2 | 6 | June | Jun | 25 | 1 | Monday | No | FY2027 | FQ1 | 2026-06
20260616 | 2026-06-16 | 2026 | 2 | Q2 | 6 | June | Jun | 25 | 2 | Tuesday | No | FY2027 | FQ1 | 2026-06
20260617 | 2026-06-17 | 2026 | 2 | Q2 | 6 | June | Jun | 25 | 3 | Wednesday | No | FY2027 | FQ1 | 2026-06
20260618 | 2026-06-18 | 2026 | 2 | Q2 | 6 | June | Jun | 25 | 4 | Thursday | No | FY2027 | FQ1 | 2026-06
20260619 | 2026-06-19 | 2026 | 2 | Q2 | 6 | June | Jun | 25 | 5 | Friday | No | FY2027 | FQ1 | 2026-06
20260620 | 2026-06-20 | 2026 | 2 | Q2 | 6 | June | Jun | 25 | 6 | Saturday | Yes | FY2027 | FQ1 | 2026-06
20260621 | 2026-06-21 | 2026 | 2 | Q2 | 6 | June | Jun | 25 | 7 | Sunday | Yes | FY2027 | FQ1 | 2026-06
20260622 | 2026-06-22 | 2026 | 2 | Q2 | 6 | June | Jun | 26 | 1 | Monday | No | FY2027 | FQ1 | 2026-06
20260623 | 2026-06-23 | 2026 | 2 | Q2 | 6 | June | Jun | 26 | 2 | Tuesday | No | FY2027 | FQ1 | 2026-06
20260624 | 2026-06-24 | 2026 | 2 | Q2 | 6 | June | Jun | 26 | 3 | Wednesday | No | FY2027 | FQ1 | 2026-06
20260625 | 2026-06-25 | 2026 | 2 | Q2 | 6 | June | Jun | 26 | 4 | Thursday | No | FY2027 | FQ1 | 2026-06
20260626 | 2026-06-26 | 2026 | 2 | Q2 | 6 | June | Jun | 26 | 5 | Friday | No | FY2027 | FQ1 | 2026-06
20260627 | 2026-06-27 | 2026 | 2 | Q2 | 6 | June | Jun | 26 | 6 | Saturday | Yes | FY2027 | FQ1 | 2026-06
20260628 | 2026-06-28 | 2026 | 2 | Q2 | 6 | June | Jun | 26 | 7 | Sunday | Yes | FY2027 | FQ1 | 2026-06
20260629 | 2026-06-29 | 2026 | 2 | Q2 | 6 | June | Jun | 27 | 1 | Monday | No | FY2027 | FQ1 | 2026-06
20260630 | 2026-06-30 | 2026 | 2 | Q2 | 6 | June | Jun | 27 | 2 | Tuesday | No | FY2027 | FQ1 | 2026-06
20260701 | 2026-07-01 | 2026 | 3 | Q3 | 7 | July | Jul | 27 | 3 | Wednesday | No | FY2027 | FQ2 | 2026-07
20260702 | 2026-07-02 | 2026 | 3 | Q3 | 7 | July | Jul | 27 | 4 | Thursday | No | FY2027 | FQ2 | 2026-07
20260703 | 2026-07-03 | 2026 | 3 | Q3 | 7 | July | Jul | 27 | 5 | Friday | No | FY2027 | FQ2 | 2026-07
20260704 | 2026-07-04 | 2026 | 3 | Q3 | 7 | July | Jul | 27 | 6 | Saturday | Yes | FY2027 | FQ2 | 2026-07
20260705 | 2026-07-05 | 2026 | 3 | Q3 | 7 | July | Jul | 27 | 7 | Sunday | Yes | FY2027 | FQ2 | 2026-07
20260706 | 2026-07-06 | 2026 | 3 | Q3 | 7 | July | Jul | 28 | 1 | Monday | No | FY2027 | FQ2 | 2026-07
20260707 | 2026-07-07 | 2026 | 3 | Q3 | 7 | July | Jul | 28 | 2 | Tuesday | No | FY2027 | FQ2 | 2026-07
20260708 | 2026-07-08 | 2026 | 3 | Q3 | 7 | July | Jul | 28 | 3 | Wednesday | No | FY2027 | FQ2 | 2026-07
20260709 | 2026-07-09 | 2026 | 3 | Q3 | 7 | July | Jul | 28 | 4 | Thursday | No | FY2027 | FQ2 | 2026-07
20260710 | 2026-07-10 | 2026 | 3 | Q3 | 7 | July | Jul | 28 | 5 | Friday | No | FY2027 | FQ2 | 2026-07
20260711 | 2026-07-11 | 2026 | 3 | Q3 | 7 | July | Jul | 28 | 6 | Saturday | Yes | FY2027 | FQ2 | 2026-07
20260712 | 2026-07-12 | 2026 | 3 | Q3 | 7 | July | Jul | 28 | 7 | Sunday | Yes | FY2027 | FQ2 | 2026-07
20260713 | 2026-07-13 | 2026 | 3 | Q3 | 7 | July | Jul | 29 | 1 | Monday | No | FY2027 | FQ2 | 2026-07
20260714 | 2026-07-14 | 2026 | 3 | Q3 | 7 | July | Jul | 29 | 2 | Tuesday | No | FY2027 | FQ2 | 2026-07
20260715 | 2026-07-15 | 2026 | 3 | Q3 | 7 | July | Jul | 29 | 3 | Wednesday | No | FY2027 | FQ2 | 2026-07
20260716 | 2026-07-16 | 2026 | 3 | Q3 | 7 | July | Jul | 29 | 4 | Thursday | No | FY2027 | FQ2 | 2026-07
20260717 | 2026-07-17 | 2026 | 3 | Q3 | 7 | July | Jul | 29 | 5 | Friday | No | FY2027 | FQ2 | 2026-07
20260718 | 2026-07-18 | 2026 | 3 | Q3 | 7 | July | Jul | 29 | 6 | Saturday | Yes | FY2027 | FQ2 | 2026-07
20260719 | 2026-07-19 | 2026 | 3 | Q3 | 7 | July | Jul | 29 | 7 | Sunday | Yes | FY2027 | FQ2 | 2026-07
20260720 | 2026-07-20 | 2026 | 3 | Q3 | 7 | July | Jul | 30 | 1 | Monday | No | FY2027 | FQ2 | 2026-07
20260721 | 2026-07-21 | 2026 | 3 | Q3 | 7 | July | Jul | 30 | 2 | Tuesday | No | FY2027 | FQ2 | 2026-07
20260722 | 2026-07-22 | 2026 | 3 | Q3 | 7 | July | Jul | 30 | 3 | Wednesday | No | FY2027 | FQ2 | 2026-07
20260723 | 2026-07-23 | 2026 | 3 | Q3 | 7 | July | Jul | 30 | 4 | Thursday | No | FY2027 | FQ2 | 2026-07
20260724 | 2026-07-24 | 2026 | 3 | Q3 | 7 | July | Jul | 30 | 5 | Friday | No | FY2027 | FQ2 | 2026-07
20260725 | 2026-07-25 | 2026 | 3 | Q3 | 7 | July | Jul | 30 | 6 | Saturday | Yes | FY2027 | FQ2 | 2026-07
20260726 | 2026-07-26 | 2026 | 3 | Q3 | 7 | July | Jul | 30 | 7 | Sunday | Yes | FY2027 | FQ2 | 2026-07
20260727 | 2026-07-27 | 2026 | 3 | Q3 | 7 | July | Jul | 31 | 1 | Monday | No | FY2027 | FQ2 | 2026-07
20260728 | 2026-07-28 | 2026 | 3 | Q3 | 7 | July | Jul | 31 | 2 | Tuesday | No | FY2027 | FQ2 | 2026-07
20260729 | 2026-07-29 | 2026 | 3 | Q3 | 7 | July | Jul | 31 | 3 | Wednesday | No | FY2027 | FQ2 | 2026-07
20260730 | 2026-07-30 | 2026 | 3 | Q3 | 7 | July | Jul | 31 | 4 | Thursday | No | FY2027 | FQ2 | 2026-07
20260731 | 2026-07-31 | 2026 | 3 | Q3 | 7 | July | Jul | 31 | 5 | Friday | No | FY2027 | FQ2 | 2026-07
20260801 | 2026-08-01 | 2026 | 3 | Q3 | 8 | August | Aug | 31 | 6 | Saturday | Yes | FY2027 | FQ2 | 2026-08
20260802 | 2026-08-02 | 2026 | 3 | Q3 | 8 | August | Aug | 31 | 7 | Sunday | Yes | FY2027 | FQ2 | 2026-08
20260803 | 2026-08-03 | 2026 | 3 | Q3 | 8 | August | Aug | 32 | 1 | Monday | No | FY2027 | FQ2 | 2026-08
20260804 | 2026-08-04 | 2026 | 3 | Q3 | 8 | August | Aug | 32 | 2 | Tuesday | No | FY2027 | FQ2 | 2026-08
20260805 | 2026-08-05 | 2026 | 3 | Q3 | 8 | August | Aug | 32 | 3 | Wednesday | No | FY2027 | FQ2 | 2026-08
20260806 | 2026-08-06 | 2026 | 3 | Q3 | 8 | August | Aug | 32 | 4 | Thursday | No | FY2027 | FQ2 | 2026-08
20260807 | 2026-08-07 | 2026 | 3 | Q3 | 8 | August | Aug | 32 | 5 | Friday | No | FY2027 | FQ2 | 2026-08
20260808 | 2026-08-08 | 2026 | 3 | Q3 | 8 | August | Aug | 32 | 6 | Saturday | Yes | FY2027 | FQ2 | 2026-08
20260809 | 2026-08-09 | 2026 | 3 | Q3 | 8 | August | Aug | 32 | 7 | Sunday | Yes | FY2027 | FQ2 | 2026-08
20260810 | 2026-08-10 | 2026 | 3 | Q3 | 8 | August | Aug | 33 | 1 | Monday | No | FY2027 | FQ2 | 2026-08
20260811 | 2026-08-11 | 2026 | 3 | Q3 | 8 | August | Aug | 33 | 2 | Tuesday | No | FY2027 | FQ2 | 2026-08
20260812 | 2026-08-12 | 2026 | 3 | Q3 | 8 | August | Aug | 33 | 3 | Wednesday | No | FY2027 | FQ2 | 2026-08
20260813 | 2026-08-13 | 2026 | 3 | Q3 | 8 | August | Aug | 33 | 4 | Thursday | No | FY2027 | FQ2 | 2026-08
20260814 | 2026-08-14 | 2026 | 3 | Q3 | 8 | August | Aug | 33 | 5 | Friday | No | FY2027 | FQ2 | 2026-08
20260815 | 2026-08-15 | 2026 | 3 | Q3 | 8 | August | Aug | 33 | 6 | Saturday | Yes | FY2027 | FQ2 | 2026-08
20260816 | 2026-08-16 | 2026 | 3 | Q3 | 8 | August | Aug | 33 | 7 | Sunday | Yes | FY2027 | FQ2 | 2026-08
20260817 | 2026-08-17 | 2026 | 3 | Q3 | 8 | August | Aug | 34 | 1 | Monday | No | FY2027 | FQ2 | 2026-08
20260818 | 2026-08-18 | 2026 | 3 | Q3 | 8 | August | Aug | 34 | 2 | Tuesday | No | FY2027 | FQ2 | 2026-08
20260819 | 2026-08-19 | 2026 | 3 | Q3 | 8 | August | Aug | 34 | 3 | Wednesday | No | FY2027 | FQ2 | 2026-08
20260820 | 2026-08-20 | 2026 | 3 | Q3 | 8 | August | Aug | 34 | 4 | Thursday | No | FY2027 | FQ2 | 2026-08
20260821 | 2026-08-21 | 2026 | 3 | Q3 | 8 | August | Aug | 34 | 5 | Friday | No | FY2027 | FQ2 | 2026-08
20260822 | 2026-08-22 | 2026 | 3 | Q3 | 8 | August | Aug | 34 | 6 | Saturday | Yes | FY2027 | FQ2 | 2026-08
20260823 | 2026-08-23 | 2026 | 3 | Q3 | 8 | August | Aug | 34 | 7 | Sunday | Yes | FY2027 | FQ2 | 2026-08
20260824 | 2026-08-24 | 2026 | 3 | Q3 | 8 | August | Aug | 35 | 1 | Monday | No | FY2027 | FQ2 | 2026-08
20260825 | 2026-08-25 | 2026 | 3 | Q3 | 8 | August | Aug | 35 | 2 | Tuesday | No | FY2027 | FQ2 | 2026-08
20260826 | 2026-08-26 | 2026 | 3 | Q3 | 8 | August | Aug | 35 | 3 | Wednesday | No | FY2027 | FQ2 | 2026-08
20260827 | 2026-08-27 | 2026 | 3 | Q3 | 8 | August | Aug | 35 | 4 | Thursday | No | FY2027 | FQ2 | 2026-08
20260828 | 2026-08-28 | 2026 | 3 | Q3 | 8 | August | Aug | 35 | 5 | Friday | No | FY2027 | FQ2 | 2026-08
20260829 | 2026-08-29 | 2026 | 3 | Q3 | 8 | August | Aug | 35 | 6 | Saturday | Yes | FY2027 | FQ2 | 2026-08
20260830 | 2026-08-30 | 2026 | 3 | Q3 | 8 | August | Aug | 35 | 7 | Sunday | Yes | FY2027 | FQ2 | 2026-08
20260831 | 2026-08-31 | 2026 | 3 | Q3 | 8 | August | Aug | 36 | 1 | Monday | No | FY2027 | FQ2 | 2026-08
20260901 | 2026-09-01 | 2026 | 3 | Q3 | 9 | September | Sep | 36 | 2 | Tuesday | No | FY2027 | FQ2 | 2026-09
20260902 | 2026-09-02 | 2026 | 3 | Q3 | 9 | September | Sep | 36 | 3 | Wednesday | No | FY2027 | FQ2 | 2026-09
20260903 | 2026-09-03 | 2026 | 3 | Q3 | 9 | September | Sep | 36 | 4 | Thursday | No | FY2027 | FQ2 | 2026-09
20260904 | 2026-09-04 | 2026 | 3 | Q3 | 9 | September | Sep | 36 | 5 | Friday | No | FY2027 | FQ2 | 2026-09
20260905 | 2026-09-05 | 2026 | 3 | Q3 | 9 | September | Sep | 36 | 6 | Saturday | Yes | FY2027 | FQ2 | 2026-09
20260906 | 2026-09-06 | 2026 | 3 | Q3 | 9 | September | Sep | 36 | 7 | Sunday | Yes | FY2027 | FQ2 | 2026-09
20260907 | 2026-09-07 | 2026 | 3 | Q3 | 9 | September | Sep | 37 | 1 | Monday | No | FY2027 | FQ2 | 2026-09
20260908 | 2026-09-08 | 2026 | 3 | Q3 | 9 | September | Sep | 37 | 2 | Tuesday | No | FY2027 | FQ2 | 2026-09
20260909 | 2026-09-09 | 2026 | 3 | Q3 | 9 | September | Sep | 37 | 3 | Wednesday | No | FY2027 | FQ2 | 2026-09
20260910 | 2026-09-10 | 2026 | 3 | Q3 | 9 | September | Sep | 37 | 4 | Thursday | No | FY2027 | FQ2 | 2026-09
20260911 | 2026-09-11 | 2026 | 3 | Q3 | 9 | September | Sep | 37 | 5 | Friday | No | FY2027 | FQ2 | 2026-09
20260912 | 2026-09-12 | 2026 | 3 | Q3 | 9 | September | Sep | 37 | 6 | Saturday | Yes | FY2027 | FQ2 | 2026-09
20260913 | 2026-09-13 | 2026 | 3 | Q3 | 9 | September | Sep | 37 | 7 | Sunday | Yes | FY2027 | FQ2 | 2026-09
20260914 | 2026-09-14 | 2026 | 3 | Q3 | 9 | September | Sep | 38 | 1 | Monday | No | FY2027 | FQ2 | 2026-09
20260915 | 2026-09-15 | 2026 | 3 | Q3 | 9 | September | Sep | 38 | 2 | Tuesday | No | FY2027 | FQ2 | 2026-09
20260916 | 2026-09-16 | 2026 | 3 | Q3 | 9 | September | Sep | 38 | 3 | Wednesday | No | FY2027 | FQ2 | 2026-09
20260917 | 2026-09-17 | 2026 | 3 | Q3 | 9 | September | Sep | 38 | 4 | Thursday | No | FY2027 | FQ2 | 2026-09
20260918 | 2026-09-18 | 2026 | 3 | Q3 | 9 | September | Sep | 38 | 5 | Friday | No | FY2027 | FQ2 | 2026-09
20260919 | 2026-09-19 | 2026 | 3 | Q3 | 9 | September | Sep | 38 | 6 | Saturday | Yes | FY2027 | FQ2 | 2026-09
20260920 | 2026-09-20 | 2026 | 3 | Q3 | 9 | September | Sep | 38 | 7 | Sunday | Yes | FY2027 | FQ2 | 2026-09
20260921 | 2026-09-21 | 2026 | 3 | Q3 | 9 | September | Sep | 39 | 1 | Monday | No | FY2027 | FQ2 | 2026-09
20260922 | 2026-09-22 | 2026 | 3 | Q3 | 9 | September | Sep | 39 | 2 | Tuesday | No | FY2027 | FQ2 | 2026-09
20260923 | 2026-09-23 | 2026 | 3 | Q3 | 9 | September | Sep | 39 | 3 | Wednesday | No | FY2027 | FQ2 | 2026-09
20260924 | 2026-09-24 | 2026 | 3 | Q3 | 9 | September | Sep | 39 | 4 | Thursday | No | FY2027 | FQ2 | 2026-09
20260925 | 2026-09-25 | 2026 | 3 | Q3 | 9 | September | Sep | 39 | 5 | Friday | No | FY2027 | FQ2 | 2026-09
20260926 | 2026-09-26 | 2026 | 3 | Q3 | 9 | September | Sep | 39 | 6 | Saturday | Yes | FY2027 | FQ2 | 2026-09
20260927 | 2026-09-27 | 2026 | 3 | Q3 | 9 | September | Sep | 39 | 7 | Sunday | Yes | FY2027 | FQ2 | 2026-09
20260928 | 2026-09-28 | 2026 | 3 | Q3 | 9 | September | Sep | 40 | 1 | Monday | No | FY2027 | FQ2 | 2026-09
20260929 | 2026-09-29 | 2026 | 3 | Q3 | 9 | September | Sep | 40 | 2 | Tuesday | No | FY2027 | FQ2 | 2026-09
20260930 | 2026-09-30 | 2026 | 3 | Q3 | 9 | September | Sep | 40 | 3 | Wednesday | No | FY2027 | FQ2 | 2026-09
20261001 | 2026-10-01 | 2026 | 4 | Q4 | 10 | October | Oct | 40 | 4 | Thursday | No | FY2027 | FQ3 | 2026-10
20261002 | 2026-10-02 | 2026 | 4 | Q4 | 10 | October | Oct | 40 | 5 | Friday | No | FY2027 | FQ3 | 2026-10
20261003 | 2026-10-03 | 2026 | 4 | Q4 | 10 | October | Oct | 40 | 6 | Saturday | Yes | FY2027 | FQ3 | 2026-10
20261004 | 2026-10-04 | 2026 | 4 | Q4 | 10 | October | Oct | 40 | 7 | Sunday | Yes | FY2027 | FQ3 | 2026-10
20261005 | 2026-10-05 | 2026 | 4 | Q4 | 10 | October | Oct | 41 | 1 | Monday | No | FY2027 | FQ3 | 2026-10
20261006 | 2026-10-06 | 2026 | 4 | Q4 | 10 | October | Oct | 41 | 2 | Tuesday | No | FY2027 | FQ3 | 2026-10
20261007 | 2026-10-07 | 2026 | 4 | Q4 | 10 | October | Oct | 41 | 3 | Wednesday | No | FY2027 | FQ3 | 2026-10
20261008 | 2026-10-08 | 2026 | 4 | Q4 | 10 | October | Oct | 41 | 4 | Thursday | No | FY2027 | FQ3 | 2026-10
20261009 | 2026-10-09 | 2026 | 4 | Q4 | 10 | October | Oct | 41 | 5 | Friday | No | FY2027 | FQ3 | 2026-10
20261010 | 2026-10-10 | 2026 | 4 | Q4 | 10 | October | Oct | 41 | 6 | Saturday | Yes | FY2027 | FQ3 | 2026-10
20261011 | 2026-10-11 | 2026 | 4 | Q4 | 10 | October | Oct | 41 | 7 | Sunday | Yes | FY2027 | FQ3 | 2026-10
20261012 | 2026-10-12 | 2026 | 4 | Q4 | 10 | October | Oct | 42 | 1 | Monday | No | FY2027 | FQ3 | 2026-10
20261013 | 2026-10-13 | 2026 | 4 | Q4 | 10 | October | Oct | 42 | 2 | Tuesday | No | FY2027 | FQ3 | 2026-10
20261014 | 2026-10-14 | 2026 | 4 | Q4 | 10 | October | Oct | 42 | 3 | Wednesday | No | FY2027 | FQ3 | 2026-10
20261015 | 2026-10-15 | 2026 | 4 | Q4 | 10 | October | Oct | 42 | 4 | Thursday | No | FY2027 | FQ3 | 2026-10
20261016 | 2026-10-16 | 2026 | 4 | Q4 | 10 | October | Oct | 42 | 5 | Friday | No | FY2027 | FQ3 | 2026-10
20261017 | 2026-10-17 | 2026 | 4 | Q4 | 10 | October | Oct | 42 | 6 | Saturday | Yes | FY2027 | FQ3 | 2026-10
20261018 | 2026-10-18 | 2026 | 4 | Q4 | 10 | October | Oct | 42 | 7 | Sunday | Yes | FY2027 | FQ3 | 2026-10
20261019 | 2026-10-19 | 2026 | 4 | Q4 | 10 | October | Oct | 43 | 1 | Monday | No | FY2027 | FQ3 | 2026-10
20261020 | 2026-10-20 | 2026 | 4 | Q4 | 10 | October | Oct | 43 | 2 | Tuesday | No | FY2027 | FQ3 | 2026-10
20261021 | 2026-10-21 | 2026 | 4 | Q4 | 10 | October | Oct | 43 | 3 | Wednesday | No | FY2027 | FQ3 | 2026-10
20261022 | 2026-10-22 | 2026 | 4 | Q4 | 10 | October | Oct | 43 | 4 | Thursday | No | FY2027 | FQ3 | 2026-10
20261023 | 2026-10-23 | 2026 | 4 | Q4 | 10 | October | Oct | 43 | 5 | Friday | No | FY2027 | FQ3 | 2026-10
20261024 | 2026-10-24 | 2026 | 4 | Q4 | 10 | October | Oct | 43 | 6 | Saturday | Yes | FY2027 | FQ3 | 2026-10
20261025 | 2026-10-25 | 2026 | 4 | Q4 | 10 | October | Oct | 43 | 7 | Sunday | Yes | FY2027 | FQ3 | 2026-10
20261026 | 2026-10-26 | 2026 | 4 | Q4 | 10 | October | Oct | 44 | 1 | Monday | No | FY2027 | FQ3 | 2026-10
20261027 | 2026-10-27 | 2026 | 4 | Q4 | 10 | October | Oct | 44 | 2 | Tuesday | No | FY2027 | FQ3 | 2026-10
20261028 | 2026-10-28 | 2026 | 4 | Q4 | 10 | October | Oct | 44 | 3 | Wednesday | No | FY2027 | FQ3 | 2026-10
20261029 | 2026-10-29 | 2026 | 4 | Q4 | 10 | October | Oct | 44 | 4 | Thursday | No | FY2027 | FQ3 | 2026-10
20261030 | 2026-10-30 | 2026 | 4 | Q4 | 10 | October | Oct | 44 | 5 | Friday | No | FY2027 | FQ3 | 2026-10
20261031 | 2026-10-31 | 2026 | 4 | Q4 | 10 | October | Oct | 44 | 6 | Saturday | Yes | FY2027 | FQ3 | 2026-10
20261101 | 2026-11-01 | 2026 | 4 | Q4 | 11 | November | Nov | 44 | 7 | Sunday | Yes | FY2027 | FQ3 | 2026-11
20261102 | 2026-11-02 | 2026 | 4 | Q4 | 11 | November | Nov | 45 | 1 | Monday | No | FY2027 | FQ3 | 2026-11
20261103 | 2026-11-03 | 2026 | 4 | Q4 | 11 | November | Nov | 45 | 2 | Tuesday | No | FY2027 | FQ3 | 2026-11
20261104 | 2026-11-04 | 2026 | 4 | Q4 | 11 | November | Nov | 45 | 3 | Wednesday | No | FY2027 | FQ3 | 2026-11
20261105 | 2026-11-05 | 2026 | 4 | Q4 | 11 | November | Nov | 45 | 4 | Thursday | No | FY2027 | FQ3 | 2026-11
20261106 | 2026-11-06 | 2026 | 4 | Q4 | 11 | November | Nov | 45 | 5 | Friday | No | FY2027 | FQ3 | 2026-11
20261107 | 2026-11-07 | 2026 | 4 | Q4 | 11 | November | Nov | 45 | 6 | Saturday | Yes | FY2027 | FQ3 | 2026-11
20261108 | 2026-11-08 | 2026 | 4 | Q4 | 11 | November | Nov | 45 | 7 | Sunday | Yes | FY2027 | FQ3 | 2026-11
20261109 | 2026-11-09 | 2026 | 4 | Q4 | 11 | November | Nov | 46 | 1 | Monday | No | FY2027 | FQ3 | 2026-11
20261110 | 2026-11-10 | 2026 | 4 | Q4 | 11 | November | Nov | 46 | 2 | Tuesday | No | FY2027 | FQ3 | 2026-11
20261111 | 2026-11-11 | 2026 | 4 | Q4 | 11 | November | Nov | 46 | 3 | Wednesday | No | FY2027 | FQ3 | 2026-11
20261112 | 2026-11-12 | 2026 | 4 | Q4 | 11 | November | Nov | 46 | 4 | Thursday | No | FY2027 | FQ3 | 2026-11
20261113 | 2026-11-13 | 2026 | 4 | Q4 | 11 | November | Nov | 46 | 5 | Friday | No | FY2027 | FQ3 | 2026-11
20261114 | 2026-11-14 | 2026 | 4 | Q4 | 11 | November | Nov | 46 | 6 | Saturday | Yes | FY2027 | FQ3 | 2026-11
20261115 | 2026-11-15 | 2026 | 4 | Q4 | 11 | November | Nov | 46 | 7 | Sunday | Yes | FY2027 | FQ3 | 2026-11
20261116 | 2026-11-16 | 2026 | 4 | Q4 | 11 | November | Nov | 47 | 1 | Monday | No | FY2027 | FQ3 | 2026-11
20261117 | 2026-11-17 | 2026 | 4 | Q4 | 11 | November | Nov | 47 | 2 | Tuesday | No | FY2027 | FQ3 | 2026-11
20261118 | 2026-11-18 | 2026 | 4 | Q4 | 11 | November | Nov | 47 | 3 | Wednesday | No | FY2027 | FQ3 | 2026-11
20261119 | 2026-11-19 | 2026 | 4 | Q4 | 11 | November | Nov | 47 | 4 | Thursday | No | FY2027 | FQ3 | 2026-11
20261120 | 2026-11-20 | 2026 | 4 | Q4 | 11 | November | Nov | 47 | 5 | Friday | No | FY2027 | FQ3 | 2026-11
20261121 | 2026-11-21 | 2026 | 4 | Q4 | 11 | November | Nov | 47 | 6 | Saturday | Yes | FY2027 | FQ3 | 2026-11
20261122 | 2026-11-22 | 2026 | 4 | Q4 | 11 | November | Nov | 47 | 7 | Sunday | Yes | FY2027 | FQ3 | 2026-11
20261123 | 2026-11-23 | 2026 | 4 | Q4 | 11 | November | Nov | 48 | 1 | Monday | No | FY2027 | FQ3 | 2026-11
20261124 | 2026-11-24 | 2026 | 4 | Q4 | 11 | November | Nov | 48 | 2 | Tuesday | No | FY2027 | FQ3 | 2026-11
20261125 | 2026-11-25 | 2026 | 4 | Q4 | 11 | November | Nov | 48 | 3 | Wednesday | No | FY2027 | FQ3 | 2026-11
20261126 | 2026-11-26 | 2026 | 4 | Q4 | 11 | November | Nov | 48 | 4 | Thursday | No | FY2027 | FQ3 | 2026-11
20261127 | 2026-11-27 | 2026 | 4 | Q4 | 11 | November | Nov | 48 | 5 | Friday | No | FY2027 | FQ3 | 2026-11
20261128 | 2026-11-28 | 2026 | 4 | Q4 | 11 | November | Nov | 48 | 6 | Saturday | Yes | FY2027 | FQ3 | 2026-11
20261129 | 2026-11-29 | 2026 | 4 | Q4 | 11 | November | Nov | 48 | 7 | Sunday | Yes | FY2027 | FQ3 | 2026-11
20261130 | 2026-11-30 | 2026 | 4 | Q4 | 11 | November | Nov | 49 | 1 | Monday | No | FY2027 | FQ3 | 2026-11
20261201 | 2026-12-01 | 2026 | 4 | Q4 | 12 | December | Dec | 49 | 2 | Tuesday | No | FY2027 | FQ3 | 2026-12
20261202 | 2026-12-02 | 2026 | 4 | Q4 | 12 | December | Dec | 49 | 3 | Wednesday | No | FY2027 | FQ3 | 2026-12
20261203 | 2026-12-03 | 2026 | 4 | Q4 | 12 | December | Dec | 49 | 4 | Thursday | No | FY2027 | FQ3 | 2026-12
20261204 | 2026-12-04 | 2026 | 4 | Q4 | 12 | December | Dec | 49 | 5 | Friday | No | FY2027 | FQ3 | 2026-12
20261205 | 2026-12-05 | 2026 | 4 | Q4 | 12 | December | Dec | 49 | 6 | Saturday | Yes | FY2027 | FQ3 | 2026-12
20261206 | 2026-12-06 | 2026 | 4 | Q4 | 12 | December | Dec | 49 | 7 | Sunday | Yes | FY2027 | FQ3 | 2026-12
20261207 | 2026-12-07 | 2026 | 4 | Q4 | 12 | December | Dec | 50 | 1 | Monday | No | FY2027 | FQ3 | 2026-12
20261208 | 2026-12-08 | 2026 | 4 | Q4 | 12 | December | Dec | 50 | 2 | Tuesday | No | FY2027 | FQ3 | 2026-12
20261209 | 2026-12-09 | 2026 | 4 | Q4 | 12 | December | Dec | 50 | 3 | Wednesday | No | FY2027 | FQ3 | 2026-12
20261210 | 2026-12-10 | 2026 | 4 | Q4 | 12 | December | Dec | 50 | 4 | Thursday | No | FY2027 | FQ3 | 2026-12
20261211 | 2026-12-11 | 2026 | 4 | Q4 | 12 | December | Dec | 50 | 5 | Friday | No | FY2027 | FQ3 | 2026-12
20261212 | 2026-12-12 | 2026 | 4 | Q4 | 12 | December | Dec | 50 | 6 | Saturday | Yes | FY2027 | FQ3 | 2026-12
20261213 | 2026-12-13 | 2026 | 4 | Q4 | 12 | December | Dec | 50 | 7 | Sunday | Yes | FY2027 | FQ3 | 2026-12
20261214 | 2026-12-14 | 2026 | 4 | Q4 | 12 | December | Dec | 51 | 1 | Monday | No | FY2027 | FQ3 | 2026-12
20261215 | 2026-12-15 | 2026 | 4 | Q4 | 12 | December | Dec | 51 | 2 | Tuesday | No | FY2027 | FQ3 | 2026-12
20261216 | 2026-12-16 | 2026 | 4 | Q4 | 12 | December | Dec | 51 | 3 | Wednesday | No | FY2027 | FQ3 | 2026-12
20261217 | 2026-12-17 | 2026 | 4 | Q4 | 12 | December | Dec | 51 | 4 | Thursday | No | FY2027 | FQ3 | 2026-12
20261218 | 2026-12-18 | 2026 | 4 | Q4 | 12 | December | Dec | 51 | 5 | Friday | No | FY2027 | FQ3 | 2026-12
20261219 | 2026-12-19 | 2026 | 4 | Q4 | 12 | December | Dec | 51 | 6 | Saturday | Yes | FY2027 | FQ3 | 2026-12
20261220 | 2026-12-20 | 2026 | 4 | Q4 | 12 | December | Dec | 51 | 7 | Sunday | Yes | FY2027 | FQ3 | 2026-12
20261221 | 2026-12-21 | 2026 | 4 | Q4 | 12 | December | Dec | 52 | 1 | Monday | No | FY2027 | FQ3 | 2026-12
20261222 | 2026-12-22 | 2026 | 4 | Q4 | 12 | December | Dec | 52 | 2 | Tuesday | No | FY2027 | FQ3 | 2026-12
20261223 | 2026-12-23 | 2026 | 4 | Q4 | 12 | December | Dec | 52 | 3 | Wednesday | No | FY2027 | FQ3 | 2026-12
20261224 | 2026-12-24 | 2026 | 4 | Q4 | 12 | December | Dec | 52 | 4 | Thursday | No | FY2027 | FQ3 | 2026-12
20261225 | 2026-12-25 | 2026 | 4 | Q4 | 12 | December | Dec | 52 | 5 | Friday | No | FY2027 | FQ3 | 2026-12
20261226 | 2026-12-26 | 2026 | 4 | Q4 | 12 | December | Dec | 52 | 6 | Saturday | Yes | FY2027 | FQ3 | 2026-12
20261227 | 2026-12-27 | 2026 | 4 | Q4 | 12 | December | Dec | 52 | 7 | Sunday | Yes | FY2027 | FQ3 | 2026-12
20261228 | 2026-12-28 | 2026 | 4 | Q4 | 12 | December | Dec | 53 | 1 | Monday | No | FY2027 | FQ3 | 2026-12
20261229 | 2026-12-29 | 2026 | 4 | Q4 | 12 | December | Dec | 53 | 2 | Tuesday | No | FY2027 | FQ3 | 2026-12
20261230 | 2026-12-30 | 2026 | 4 | Q4 | 12 | December | Dec | 53 | 3 | Wednesday | No | FY2027 | FQ3 | 2026-12
20261231 | 2026-12-31 | 2026 | 4 | Q4 | 12 | December | Dec | 53 | 4 | Thursday | No | FY2027 | FQ3 | 2026-12

## DIM_Team
PersonID | FullName | Role | Seniority | Team | Department | DailyRatePlan_GBP | IsContractor | SkillTags | ProjectAssignments
T001 | Ariful Haque | Portfolio Analyst | Mid | ECS PMO | IT PMO | 650 | FALSE | Power BI; Azure DevOps; PMP; RAID; Financial Reporting | P002; P003
T002 | Sarah Chen | Digital Product Manager | Senior | Digital | Digital & IT | 850 | FALSE | Agile; Scrum; Roadmap; Stakeholder Management | P001; P010
T003 | James Patel | Cloud & Azure Engineer | Senior | Infrastructure | IT Operations | 920 | TRUE | Azure; Azure AD; MSAL; DevOps; Networking | P001; P002; P004
T004 | Nina Sharma | Cyber Security Lead | Senior | Security | IT Security | 880 | FALSE | ISO27001; NIST; Pen Testing; Compliance; Risk | P005
T005 | David Kim | SAP Technical Lead | Senior | Finance Systems | Finance & IT | 950 | TRUE | SAP S/4HANA; ABAP; Integration; Finance | P008
T006 | Emma Collins | Business Analyst | Mid | Corporate Systems | Human Resources | 600 | FALSE | Requirements; UAT; Process Mapping; Visio | P007
T007 | Tom Bradley | Delivery Manager | Senior | Field Services | Field Operations | 800 | FALSE | Prince2; Agile; Field Operations; Change Management | P006
T008 | Dev Team A | Front-End Development Team | Mid | Digital | Digital & IT | 720 | TRUE | React; TypeScript; CSS; Accessibility; Azure Static Web Apps | P001
T009 | Dev Team B | Back-End Development Team | Mid | Digital | Digital & IT | 760 | TRUE | Python; Azure Functions; API Integration; SQL | P001; P004
T010 | Cloud Admin | Cloud Operations Engineer | Mid | Infrastructure | IT Operations | 700 | TRUE | Azure Policy; Terraform; Networking; Cost Management | P002; P009
T011 | Mark Hughes | IT Programme Director | Director | IT Leadership | Digital & IT | 1200 | FALSE | Portfolio Management; Strategy; Governance; Stakeholder | P001; P002; P005; P010
T012 | Lisa Ward | Head of IT PMO | Director | ECS PMO | IT PMO | 1100 | FALSE | Portfolio Governance; RAID; Finance; Resource Planning | P003; P004

## FACT_Benefits
BenefitID | ProjectID | BenefitName | BenefitType | BenefitOwner | PlannedValue_GBP | ForecastValue_GBP | ActualisedValue_GBP | PlannedEnablementDate | ActualEnablementDate | PlannedRealisationDate | ActualRealisationDate | RealisationStatus | ConfidenceLevel | Notes
BEN-001 | P001 | Reduction in call centre volume — digital self-service | Cost Saving | Mark Hughes | 420000 | 390000 | 0 | 2026-09-30 |  | 2026-12-31 |  | Planned | High | Target: 15% reduction in call volume. Measured by call centre KPI report post go-live.
BEN-002 | P001 | Improved customer satisfaction (NPS increase) | Customer Experience | Mark Hughes | 0 | 0 | 0 | 2026-09-30 |  | 2026-12-31 |  | Planned | Medium | Target: NPS increase from 42 to 57. Quarterly survey post go-live.
BEN-003 | P002 | Cloud infrastructure cost reduction vs. on-prem | Cost Saving | Mark Hughes | 380000 | 320000 | 0 | 2026-12-31 |  | 2027-03-31 |  | Planned | Medium | Target: 30% opex reduction. Baseline set at £420k/yr on-prem.
BEN-004 | P002 | Improved IT system availability (uptime) | Risk Reduction | Mark Hughes | 0 | 0 | 0 | 2026-12-31 |  | 2027-06-30 |  | Planned | High | Target: 99.9% uptime vs current 99.1%. SLA enforced via Azure Monitor.
BEN-005 | P003 | MI pack production time reduction | Efficiency | Lisa Ward | 45000 | 52000 | 28000 | 2026-03-29 | 2026-03-29 | 2026-06-30 |  | Enabled | High | Actual: Time reduced from 4hrs to 45min confirmed by PMO. Annualised saving £52k.
BEN-006 | P003 | Improved reporting accuracy — fewer errors | Quality | Lisa Ward | 15000 | 18000 | 0 | 2026-05-31 |  | 2026-09-30 |  | Planned | High | Target: 0 MI pack errors requiring rework. Currently 2-3 per month.
BEN-007 | P005 | Regulatory fine avoidance | Risk Reduction | Mark Hughes | 2500000 | 2500000 | 0 | 2026-07-31 |  | 2026-07-31 |  | Planned | High | ICO fine for non-compliance estimated £2.5M. Compliance avoids this exposure.
BEN-008 | P005 | Cyber incident cost reduction | Risk Reduction | Nina Sharma | 180000 | 180000 | 0 | 2026-07-31 |  | 2026-12-31 |  | Planned | Medium | Average breach cost £180k. Improved posture reduces probability by est. 40%.
BEN-009 | P006 | Field engineer productivity improvement | Efficiency | Rachel Evans | 95000 | 110000 | 110000 | 2026-04-15 | 2026-04-15 | 2026-07-31 |  | Enabled | High | App deployed. Engineers saving avg 45 min/day. 140 engineers = £110k/yr.
BEN-010 | P008 | Finance reporting automation — headcount saving | Cost Saving | Simon Grant | 120000 | 105000 | 0 | 2026-07-21 |  | 2026-09-30 |  | At Risk | Low | Delayed go-live reduces benefit realisation window. Revised to £105k.